## Dashboard
PANDA SHOES INDUSTRY LTD — PURCHASE & PROCUREMENT PERFORMANCE DASHBOARD
Report date: 15 Oct 2026 ¦ Values in BDT Lakh (1 Lakh = 1,00,000) ¦ Source: Purchase_Register (auto-refresh)
PRs Raised |  |  |  | POs Issued |  |  |  | Committed Spend |  |  |  | Paid to Suppliers |  |  |  |  | Outstanding Payable
45 |  |  |  | 39 |  |  |  | 565.19 |  |  |  | 338.4732 |  |  |  |  | 226.7168
Overdue Payable |  |  |  | % Paid |  |  |  | OPEX Committed |  |  |  | CAPEX Committed |  |  |  |  | Budget Utilisation
33.2376 |  |  |  | 59.89% |  |  |  | 439.6495 |  |  |  | 125.5405 |  |  |  |  | 44.19%
Net Price Variance vs Budget |  |  |  | OTIF Delivery |  |  |  | Avg Days PR → Approval |  |  |  | Avg Days Approval → PO |  |  |  |  | Avg Lead Time PO → In-house
9.6836 |  |  |  | 50% |  |  |  | 2.9286 |  |  |  | 3.0769 |  |  |  |  | 21.7647
Avg Full Cycle PR → Close |  |  |  | Awaiting Approval |  |  |  | Open POs (not in-house) |  |  |  | Late Deliveries (open + closed) |  |  |  |  | PO without Approval (control breach)
28.0882 |  |  |  | 3 |  |  |  | 5 |  |  |  | 12 |  |  |  |  | 0
Savings vs Budget Price |  |  |  | Pending In-house Value |  |  |  | Paid Ahead of Receipt (risk) |  |  |  | In-Full Delivery Rate |  |  |  |  | High-Priority Actions
3.7347 |  |  |  | 101.0574 |  |  |  | 42.7851 |  |  |  | 79.41% |  |  |  |  | 12
ACTIONS: 22 line(s) — see Action_Tracker |  |  |  | DATA CHECK: 1 register line(s) need correction — see Data Check column | [8 empty] | PENDING IN-HOUSE: 5 open PO line(s), BDT 101.06 Lakh ¦ Short closed: 7
MANAGEMENT HIGHLIGHTS — written automatically from the latest data
▸ Spend: BDT 565.19 Lakh committed on 39 POs — 60% paid; BDT 226.72 Lakh outstanding, of which BDT 33.24 Lakh is overdue.
▸ Concentration: largest supplier is Savar Leather Works Ltd with 32% of spend — moderately concentrated (HHI 1,959). Top category: Leather & Upper at 32%; 4 A-class categories carry 89% of spend.
▸ Supplier performance: 3 rated A-Preferred, 4 B-Approved, 3 C-Review. Best: Chattogram Packaging Ltd (100); weakest: Gazipur Chem Trade (51).
▸ Delivery: OTIF 50%, in-full 79%, average lead time 22 days. 0 open PO(s) are late; BDT 101.06 Lakh of material still to come in-house; 7 line(s) short-closed.
▸ Budget & price: 1 department(s) over budget, 1 on watch (overall 44% used). Buying vs budget price: BDT 3.73 Lakh saved, BDT 13.42 Lakh overspent; 6 line(s) bought dearer than the previous PO.
▸ Cash & risk: BDT 42.79 Lakh paid ahead of goods received; 12 high, 7 medium and 3 low priority action line(s) open; 0 PO(s) without approval.
CHART DATA (auto-calculated — feeds the charts above)
Category | Committed (Lakh) | Paid (Lakh) | Outstanding (Lakh) | Spend Type | Committed (Lakh) | Finance Status | PO Lines | Value (Lakh) | Month | PO Value (Lakh) | Paid (Lakh) | Due (Lakh) |  | Supplier (top 10 by spend) | Spend (Lakh) | OTIF % | Score
Leather & Upper | 178.2995 | 119.6353 | 58.6642 | OPEX | 439.6495 | Not Paid | 5 | 44.9152 | Jul-26 | 49.3303 | 33.5764 | 0 |  | Savar Leather Works Ltd | 178.2995 | 60% | 66
Machinery & Equipment | 117.9223 | 66.9987 | 50.9236 | CAPEX | 125.5405 | Initial / Advance Paid | 9 | 182.6326 | Aug-26 | 165.1915 | 116.037 | 14.8329 |  | Dongguan Sole Tech Co. | 105.899 | 100% | 98
Sole & Bottom | 103.9877 | 35.3131 | 68.6746 |  |  | Partially Paid | 5 | 33.6653 | Sep-26 | 95.1401 | 93.2188 | 16.9554 |  | Jiangsu Footwear Machinery Co. | 101.8471 | 0% | 53
Synthetic & Textile | 101.0576 | 81.0135 | 20.0441 | Stage | Lines | Fully Paid | 20 | 244.9576 | Oct-26 | 68.9282 | 39.8652 | 63.3745 |  | Bengal Sole Industries | 86.4622 | 50% | 64
Chemicals & Adhesives | 23.8392 | 9.3557 | 14.4835 | Awaiting Approval | 3 |  |  |  | Nov-26 | 0 | 0 | 72.5348 |  | Dhaka Spares & Tools | 25.8853 | 33.33% | 65
Trims & Accessories | 13.3104 | 7.2862 | 6.0242 | Approved - PO Pending | 2 | Aging Bucket | Outstanding (Lakh) |  | Dec-26 | 0 | 0 | 0 |  | Gazipur Chem Trade | 23.8392 | 50% | 51
Packaging | 9.3451 | 9.3451 | 0 | PO Issued - Awaiting Delivery | 4 | Not Yet Due | 134.46 |  | Jan-27 | 0 | 0 | 0 |  | Delta Thread & Trims | 13.3104 | 40% | 65
IT Equipment | 7.6182 | 3.8091 | 3.8091 | Receiving In-house | 1 | 1-30 Days | 13.8028 |  | Feb-27 | 0 | 0 | 0 |  | Narayanganj Board Mills | 12.684 | 0% | 59
Safety & Facility | 6.1813 | 3.658 | 2.5232 | In-house Closed - Payment Due | 16 | 31-60 Days | 5.6887 |  | Mar-27 | 0 | 0 | 0 |  | Chattogram Packaging Ltd | 9.3451 | 100% | 100
Spare Parts | 3.6289 | 2.0585 | 1.5704 | Closed | 18 | 61-90 Days | 13.7462 |  | Apr-27 | 0 | 0 | 0 |  | Tech Point BD | 7.6182 | 100% | 88
|  |  |  | Rejected | 1 | 90+ Days | 0 |  | May-27 | 0 | 0 | 0
[6 empty] | No Due Date | 59.0192 |  | Jun-27 | 0 | 0 | 0
[9 empty] | Department | Budget (Lakh) | Committed (Lakh) | Utilisation
[9 empty] | Lasting & Assembly | 340 | 100.6934 | 29.62%
[9 empty] | Cutting | 320 | 279.357 | 87.3%
[9 empty] | Stitching | 150 | 13.3104 | 8.874%
[9 empty] | Finishing & Packing | 140 | 9.3451 | 6.675%
[9 empty] | Maintenance | 100 | 120.3832 | 120.4%
[9 empty] | Product Development | 60 | 0 | 0%
[9 empty] | IT | 30 | 7.6182 | 25.39%
[9 empty] | Store & Warehouse | 30 | 0 | 0%
[9 empty] | Compliance & HSE | 25 | 6.1813 | 24.73%
[9 empty] | Admin | 20 | 0 | 0%

## Action_Tracker
Action Tracker — what needs attention today
Automatic list from the Purchase Register, sorted High → Medium → Low priority. Fix the cause in the register and the line drops off this list.
|  | High priority |  | Medium priority | Low priority | Overdue payable (BDT) |  | Paid ahead of receipt (BDT) | Late open POs
|  | 12 |  | 7 | 3 | 3323763.24 |  | 4278510 | 0
# | Reg. row | Priority | PR No | Item / Material | Supplier | Department | Current Stage | Pending Material Status | Outstanding Payable (BDT) | Paid Ahead of Receipt (BDT) | Action Required
1 | 2 | High | PSIL-PR-2026-0002 | Suede Split Leather | Savar Leather Works Ltd | Cutting | Closed | All In-house | 0 | 0 | QC rejected: return / replace;
2 | 5 | High | PSIL-PR-2026-0005 | Rubber Outsole – Men's Derby | Bengal Sole Industries | Lasting & Assembly | In-house Closed - Payment Due | Short Closed - 561 pair not received | 1074150 | 0 | Pay supplier: 71 days overdue; Short closed: claim balance / credit note;
3 | 8 | High | PSIL-PR-2026-0008 | PU Adhesive (Solvent Based) | Gazipur Chem Trade | Lasting & Assembly | Closed | Short Closed - 36 kg not received | 0 | 16680 | Short closed: claim balance / credit note BDT 16,680; QC rejected: return / replace;
4 | 10 | High | PSIL-PR-2026-0010 | Bonded Nylon Thread | Delta Thread & Trims | Stitching | In-house Closed - Payment Due | Short Closed - 49 cone not received | 300468 | 0 | Pay supplier: 70 days overdue; Short closed: claim balance / credit note;
5 | 11 | High | PSIL-PR-2026-0011 | Metal Eyelets & Hooks | Delta Thread & Trims | Stitching | In-house Closed - Payment Due | All In-house | 108675 | 0 | Pay supplier: 54 days overdue;
6 | 12 | High | PSIL-PR-2026-0012 | Waxed Cotton Laces | Delta Thread & Trims | Stitching | Closed | All In-house | 0 | 0 | QC rejected: return / replace;
7 | 13 | High | PSIL-PR-2026-0013 | Cellulose Insole Board | Narayanganj Board Mills | Cutting | In-house Closed - Payment Due | All In-house | 352800 | 0 | Pay supplier: 31 days overdue;
8 | 17 | High | PSIL-PR-2026-0017 | Sewing Machine Needles & Spares | Dhaka Spares & Tools | Maintenance | In-house Closed - Payment Due | All In-house | 40248 | 0 | Pay supplier: 25 days overdue; QC rejected: return / replace;
9 | 18 | High | PSIL-PR-2026-0018 | Safety PPE (Masks, Gloves, Goggles) | Dhaka Spares & Tools | Compliance & HSE | In-house Closed - Payment Due | All In-house | 107392.5 | 0 | Pay supplier: 36 days overdue;
10 | 24 | High | PSIL-PR-2026-0024 | Pig Lining Leather | Savar Leather Works Ltd | Cutting | In-house Closed - Payment Due | All In-house | 814188.17 | 0 | Pay supplier: 22 days overdue; QC rejected: return / replace;
11 | 33 | High | PSIL-PR-2026-0033 | Cow Nappa Upper Leather | Savar Leather Works Ltd | Cutting | Closed | Short Closed - 915 sqft not received | 0 | 281308 | Short closed: claim balance / credit note BDT 281,308;
12 | 34 | High | PSIL-PR-2026-0034 | PU Adhesive (Solvent Based) | Gazipur Chem Trade | Lasting & Assembly | In-house Closed - Payment Due | All In-house | 563730 | 0 | QC rejected: return / replace;
13 | 19 | Medium | PSIL-PR-2026-0019 | Computerised Post-bed Sewing Machine | Jiangsu Footwear Machinery Co. | Maintenance | In-house Closed - Payment Due | Short Closed - 1 unit not received | 2779880.68 | 0 | Short closed: claim balance / credit note;
14 | 23 | Medium | PSIL-PR-2026-0023 | Laptop for PPC & Costing Team | Tech Point BD | IT | In-house Closed - Payment Due | All In-house | 380910.07 | 0 | Pay supplier: 19 days overdue;
15 | 30 | Medium | PSIL-PR-2026-0030 | Safety PPE (Masks, Gloves, Goggles) | Dhaka Spares & Tools | Compliance & HSE | In-house Closed - Payment Due | All In-house | 144931.5 | 0 | Pay supplier: 12 days overdue;
16 | 31 | Medium | PSIL-PR-2026-0031 | PU Adhesive (Solvent Based) | Gazipur Chem Trade | Lasting & Assembly | In-house Closed - Payment Due | Short Closed - 34 kg not received | 612105 | 0 | Short closed: claim balance / credit note;
17 | 32 | Medium | PSIL-PR-2026-0032 | TPR Outsole – Ladies Casual | Bengal Sole Industries | Lasting & Assembly | In-house Closed - Payment Due | Short Closed - 167 pair not received | 859320 | 0 | Short closed: claim balance / credit note;
18 | 39 | Medium | PSIL-PR-2026-0039 | Rubber Outsole – Men's Derby | Bengal Sole Industries | Lasting & Assembly | Awaiting Approval | No PO Yet | 2440830 | 0 | Get approval: PR waiting 21 days;
19 | 41 | Medium | PSIL-PR-2026-0041 | Rubber Outsole – Men's Derby | Bengal Sole Industries | Lasting & Assembly | Approved - PO Pending | No PO Yet | 1688400 | 0 | Issue PO: approved 9 days ago; Negotiate price: 9% above budget;
20 | 43 | Low | PSIL-PR-2026-0043 | Pig Lining Leather | Savar Leather Works Ltd | Cutting | Approved - PO Pending | No PO Yet | 1383379.2 | 0 | Issue PO: approved 4 days ago;
21 | 44 | Low | PSIL-PR-2026-0044 | Primer & Halogenating Agent | Gazipur Chem Trade | Lasting & Assembly | Awaiting Approval | No PO Yet | 272512.5 | 0 | Get approval: PR waiting 6 days;
22 | 45 | Low | PSIL-PR-2026-0045 | Heel Counter Stiffener (demo: incomplete entry) |  |  | Awaiting Approval | No PO Yet | 0 | 0 | Fix data entry (see Data Check);

## Purchase_Register
PANDA SHOES INDUSTRY LTD — PURCHASE TRACKING REGISTER (PR → Approval → PO → In-house → Payment)
BLACK cells with WHITE text = data entry (only these can be typed in). ORANGE = required input missing for this stage. GREY = automatic formula (locked). Check the 'Data Check' column — every line should read OK. Capacity: rows 6–205.
✎ INPUT | ✎ INPUT | ✎ INPUT | ✎ INPUT | ✎ INPUT | ✎ INPUT | ✎ INPUT | ✎ INPUT | ✎ INPUT | ✎ INPUT | ✎ INPUT | ✎ INPUT | ✎ INPUT | ✎ INPUT | ✎ INPUT | ✎ INPUT | ✎ INPUT | ✎ INPUT | ✎ INPUT | ✎ INPUT | AUTO | ✎ INPUT | AUTO | AUTO | AUTO | AUTO | AUTO | AUTO | ✎ INPUT | AUTO | ✎ INPUT | ✎ INPUT | ✎ INPUT | ✎ INPUT | AUTO | AUTO | AUTO | AUTO | AUTO | ✎ INPUT | ✎ INPUT | AUTO | AUTO | ✎ INPUT | ✎ INPUT | ✎ INPUT | AUTO | AUTO | AUTO | AUTO | ✎ INPUT | AUTO | AUTO | AUTO | AUTO | AUTO | AUTO | ✎ INPUT | ✎ INPUT | ✎ INPUT | AUTO | AUTO | AUTO | AUTO | AUTO | ✎ INPUT
1 · REQUISITION & OPEX/CAPEX APPROVAL | [11 empty] | 2 · PURCHASE ORDER & VALUE | [17 empty] | 3 · FINANCE STATUS & PAYABLES | [12 empty] | 4 · IN-HOUSE RECEIVING & CYCLE TIME | [13 empty] | 5 · MATERIAL APPROVAL & STAGE
PR No | PR Received Date | Department | Requested By | Item / Material Purchased | Category | Spec / Size / Colour | Spend Type (OPEX / CAPEX) | OPEX / CAPEX Approval Ref | Approval Date | Approval Status | Approved By | Supplier | Local / Import | PO No | PO Date | Order Quantity | UOM | Unit Price (PO Currency) | Currency | FX Rate to BDT | Budget / Standard Unit Price (BDT) | PO Value (BDT) | Unit Price (BDT) | Previous PO Unit Price — Same Item (BDT) | Price Change vs Previous PO % | Price Variance vs Budget (BDT) | Price Variance % | VAT / AIT / Duty % | Total Price incl. Tax (BDT) | Payment Terms | Initial / Advance Paid (BDT) | Interim Payment (BDT) | Closing Payment (BDT) | Total Paid (BDT) | % of Payment | Outstanding Payable (BDT) | Paid Ahead of Receipt (BDT) | Finance Status | Last Payment Date | Next Payment Due Date | Days Payment Overdue | Payable Aging Bucket | Supplier Committed Delivery Date | Starting to In-house Date | Qty Received In-house | Received % | Pending Qty to In-house | Pending In-house Value (BDT) | Pending Material Status | Final In-house Closing Date | Days PR → Approval | Days Approval → PO | Lead Time PO → In-house Close (days) | Total Cycle PR → Close (days) | Delivery Delay (days) | OTIF | QC / Material Approval | Approved Material Photo — File / Link | Approved Material Picture | Current Stage | Data Check (auto) | Action Required (auto) | Action Priority | Action Sort Key | Remarks
PSIL-PR-2026-0001 | 2026-06-02 | Cutting | Cutting Manager | Cow Nappa Upper Leather | Leather & Upper | 1.2–1.4 mm, Black | OPEX | OPX-2026-101 | 2026-06-03 | Approved | GM Operations | Savar Leather Works Ltd | Local | PSIL-PO-2026-0001 | 2026-06-08 | 10500 | sqft | 2.35 | USD | 122 | 278.93 | 3010350 | 286.7 |  |  | 81585 | 2.786% | 5% | 3160867.5 | 30% Advance / 70% after In-house | 948260.25 |  | 2212607.25 | 3160867.5 | 100% | 0 | 0 | Fully Paid | 2026-06-30 |  |  |  | 2026-06-18 | 2026-06-15 | 10500 | 100% | 0 | 0 | All In-house | 2026-06-15 | 1 | 5 | 7 | 13 | 0 | OTIF | Approved | Photos\PSIL-PR-2026-0001.jpg |  | Closed | OK
PSIL-PR-2026-0002 | 2026-06-05 | Cutting | Cutting Manager | Suede Split Leather | Leather & Upper | 1.6 mm, Taupe | OPEX | OPX-2026-102 | 2026-06-07 | Approved | CFO | Savar Leather Works Ltd | Local | PSIL-PO-2026-0002 | 2026-06-12 | 4500 | sqft | 1.76 | USD | 122 | 196.76 | 966240 | 214.72 |  |  | 80820 | 9.128% | 5% | 1014552 | 100% Advance | 1014552 |  |  | 1014552 | 100% | 0 | 0 | Fully Paid | 2026-06-13 |  |  |  | 2026-07-01 | 2026-06-25 | 4500 | 100% | 0 | 0 | All In-house | 2026-06-26 | 2 | 5 | 14 | 21 | 0 | OTIF | Rejected |  |  | Closed | OK | QC rejected: return / replace; | High | 10007
PSIL-PR-2026-0003 | 2026-06-08 | Cutting | Cutting Manager | Pig Lining Leather | Leather & Upper | 0.8 mm, Natural | OPEX | OPX-2026-103 | 2026-06-10 | Approved | CFO | Savar Leather Works Ltd | Local | PSIL-PO-2026-0003 | 2026-06-15 | 8400 | sqft | 97 | BDT | 1 | 95.4 | 814800 | 97 |  |  | 13440 | 1.677% | 5% | 855540 | Credit 30 Days |  |  | 855540 | 855540 | 100% | 0 | 0 | Fully Paid | 2026-08-02 |  |  |  | 2026-07-04 | 2026-07-03 | 8400 | 100% | 0 | 0 | All In-house | 2026-07-03 | 2 | 5 | 18 | 25 | 0 | OTIF | Approved | Photos\PSIL-PR-2026-0003.jpg |  | Closed | OK
PSIL-PR-2026-0004 | 2026-06-11 | Cutting | Cutting Manager | PU Synthetic Leather | Synthetic & Textile | 1.0 mm, White, 54" | OPEX | OPX-2026-104 | 2026-06-15 | Approved | GM Operations | Dongguan Sole Tech Co. | Import | PSIL-PO-2026-0004 | 2026-06-18 | 7400 | meter | 3.11 | USD | 122 | 373.98 | 2807708 | 379.42 |  |  | 40256 | 1.455% | 15% | 3228864.2 | LC at Sight |  |  | 3228864.2 | 3228864.2 | 100% | 0 | 0 | Fully Paid | 2026-07-20 |  |  |  | 2026-07-30 | 2026-07-26 | 7400 | 100% | 0 | 0 | All In-house | 2026-07-27 | 4 | 3 | 39 | 46 | 0 | OTIF | Approved | Photos\PSIL-PR-2026-0004.jpg |  | Closed | OK
PSIL-PR-2026-0005 | 2026-06-14 | Lasting & Assembly | Lasting Manager | Rubber Outsole – Men's Derby | Sole & Bottom | Size 39–45, Black | OPEX | OPX-2026-105 | 2026-06-15 | Approved | CFO | Bengal Sole Industries | Local | PSIL-PO-2026-0005 | 2026-06-20 | 11000 | pair | 186 | BDT | 1 | 186.21 | 2046000 | 186 |  |  | -2310 | -0.1128% | 5% | 2148300 | Credit 30 Days |  | 1074150 |  | 1074150 | 50% | 1074150 | 0 | Partially Paid | 2026-08-05 | 2026-08-05 | 71 | 61-90 Days | 2026-07-06 | 2026-07-05 | 10439 | 94.9% | 561 | 109563.3 | Short Closed - 561 pair not received | 2026-07-06 | 1 | 5 | 16 | 22 | 0 | Not OTIF | Approved | Photos\PSIL-PR-2026-0005.jpg |  | In-house Closed - Payment Due | OK | Pay supplier: 71 days overdue; Short closed: claim balance / credit note; | High | 10010 | Price above budget — CFO note on file
PSIL-PR-2026-0006 | 2026-06-17 | Lasting & Assembly | Lasting Manager | TPR Outsole – Ladies Casual | Sole & Bottom | Size 35–41, Beige | OPEX | OPX-2026-106 | 2026-06-21 | Approved | CFO | Bengal Sole Industries | Local | PSIL-PO-2026-0006 | 2026-06-22 | 6800 | pair | 125 | BDT | 1 | 120.68 | 850000 | 125 |  |  | 29376 | 3.58% | 5% | 892500 | 100% Advance | 892500 |  |  | 892500 | 100% | 0 | 0 | Fully Paid | 2026-06-23 |  |  |  | 2026-07-06 | 2026-07-01 | 6800 | 100% | 0 | 0 | All In-house | 2026-07-01 | 4 | 1 | 9 | 14 | 0 | OTIF | Approved | Photos\PSIL-PR-2026-0006.jpg |  | Closed | OK
PSIL-PR-2026-0007 | 2026-06-21 | Lasting & Assembly | Lasting Manager | EVA Midsole Sheet | Sole & Bottom | 6 mm, Shore 45A | OPEX | OPX-2026-107 | 2026-06-25 | Approved | GM Operations | Dongguan Sole Tech Co. | Import | PSIL-PO-2026-0007 | 2026-06-26 | 4800 | sheet | 10.1 | CNY | 17 | 159.41 | 824160 | 171.7 |  |  | 58992 | 7.71% | 15% | 947784 | LC at Sight |  |  | 947784 | 947784 | 100% | 0 | 0 | Fully Paid | 2026-08-04 |  |  |  | 2026-08-14 | 2026-08-13 | 4800 | 100% | 0 | 0 | All In-house | 2026-08-14 | 4 | 1 | 49 | 54 | 0 | OTIF | Approved | Photos\PSIL-PR-2026-0007.jpg |  | Closed | OK
PSIL-PR-2026-0008 | 2026-06-23 | Lasting & Assembly | Lasting Manager | PU Adhesive (Solvent Based) | Chemicals & Adhesives | 15 kg drum | OPEX | OPX-2026-108 | 2026-06-27 | Approved | CFO | Gazipur Chem Trade | Local | PSIL-PO-2026-0008 | 2026-06-29 | 1100 | kg | 431 | BDT | 1 | 407.49 | 474100 | 431 |  |  | 25861 | 5.769% | 7.5% | 509657.5 | 100% Advance | 509657.5 |  |  | 509657.5 | 100% | 0 | 16680 | Fully Paid | 2026-06-30 |  |  |  | 2026-07-16 | 2026-07-24 | 1064 | 96.73% | 36 | 16679.7 | Short Closed - 36 kg not received | 2026-07-26 | 4 | 2 | 27 | 33 | 10 | Not OTIF | Rejected |  |  | Closed | OK | Short closed: claim balance / credit note BDT 16,680; QC rejected: return / replace; | High | 10013
PSIL-PR-2026-0009 | 2026-06-27 | Lasting & Assembly | Lasting Manager | Primer & Halogenating Agent | Chemicals & Adhesives | Rubber sole primer | OPEX | OPX-2026-109 | 2026-07-01 | Approved | CFO | Gazipur Chem Trade | Local | PSIL-PO-2026-0009 | 2026-07-03 | 700 | kg | 566 | BDT | 1 | 525.7 | 396200 | 566 |  |  | 28210 | 7.666% | 7.5% | 425915 | Credit 30 Days |  |  | 425915 | 425915 | 100% | 0 | 0 | Fully Paid | 2026-08-16 |  |  |  | 2026-07-14 | 2026-07-10 | 700 | 100% | 0 | 0 | All In-house | 2026-07-11 | 4 | 2 | 8 | 14 | 0 | OTIF | Approved | Photos\PSIL-PR-2026-0009.jpg |  | Closed | OK
PSIL-PR-2026-0010 | 2026-06-29 | Stitching | Stitching Manager | Bonded Nylon Thread | Trims & Accessories | Tex 70, Black | OPEX | OPX-2026-110 | 2026-07-02 | Approved | GM Operations | Delta Thread & Trims | Local | PSIL-PO-2026-0010 | 2026-07-04 | 1400 | cone | 292 | BDT | 1 | 308.49 | 408800 | 292 |  |  | -23086 | -5.345% | 5% | 429240 | 30% Advance / 70% after In-house | 128772 |  |  | 128772 | 30% | 300468 | 0 | Initial / Advance Paid | 2026-07-06 | 2026-08-06 | 70 | 61-90 Days | 2026-07-25 | 2026-07-19 | 1351 | 96.5% | 49 | 15023.4 | Short Closed - 49 cone not received | 2026-07-22 | 3 | 2 | 18 | 23 | 0 | Not OTIF | Approved | Photos\PSIL-PR-2026-0010.jpg |  | In-house Closed - Payment Due | OK | Pay supplier: 70 days overdue; Short closed: claim balance / credit note; | High | 10015
PSIL-PR-2026-0011 | 2026-07-02 | Stitching | Stitching Manager | Metal Eyelets & Hooks | Trims & Accessories | Antique brass, 5 mm | OPEX | OPX-2026-111 | 2026-07-06 | Approved | CFO | Delta Thread & Trims | Local | PSIL-PO-2026-0011 | 2026-07-08 | 900 | gross | 230 | BDT | 1 | 229.75 | 207000 | 230 |  |  | 225 | 0.1088% | 5% | 217350 | Credit 30 Days |  | 108675 |  | 108675 | 50% | 108675 | 0 | Partially Paid | 2026-08-22 | 2026-08-22 | 54 | 31-60 Days | 2026-07-19 | 2026-07-22 | 900 | 100% | 0 | 0 | All In-house | 2026-07-23 | 4 | 2 | 15 | 21 | 4 | Not OTIF | Approved | Photos\PSIL-PR-2026-0011.jpg |  | In-house Closed - Payment Due | OK | Pay supplier: 54 days overdue; | High | 10016
PSIL-PR-2026-0012 | 2026-07-06 | Stitching | Stitching Manager | Waxed Cotton Laces | Trims & Accessories | 120 cm, Brown | OPEX | OPX-2026-112 | 2026-07-07 | Approved | CFO | Delta Thread & Trims | Local | PSIL-PO-2026-0012 | 2026-07-12 | 11700 | pair | 15.15 | BDT | 1 | 14.1 | 177255 | 15.15 |  |  | 12285 | 7.447% | 5% | 186117.75 | Credit 30 Days |  |  | 186117.75 | 186117.75 | 100% | 0 | 0 | Fully Paid | 2026-08-27 |  |  |  | 2026-07-28 | 2026-07-26 | 11700 | 100% | 0 | 0 | All In-house | 2026-07-28 | 1 | 5 | 16 | 22 | 0 | OTIF | Rejected |  |  | Closed | OK | QC rejected: return / replace; | High | 10017
PSIL-PR-2026-0013 | 2026-07-08 | Cutting | Cutting Manager | Cellulose Insole Board | Synthetic & Textile | 2.0 mm, 1x1.5 m | OPEX | OPX-2026-113 | 2026-07-11 | Approved | GM Operations | Narayanganj Board Mills | Local | PSIL-PO-2026-0013 | 2026-07-15 | 2000 | sheet | 336 | BDT | 1 | 332.74 | 672000 | 336 |  |  | 6520 | 0.9797% | 5% | 705600 | Credit 30 Days |  | 352800 |  | 352800 | 50% | 352800 | 0 | Partially Paid | 2026-09-14 | 2026-09-14 | 31 | 31-60 Days | 2026-08-07 | 2026-08-15 | 2000 | 100% | 0 | 0 | All In-house | 2026-08-15 | 3 | 4 | 31 | 38 | 8 | Not OTIF | Approved | Photos\PSIL-PR-2026-0013.jpg |  | In-house Closed - Payment Due | OK | Pay supplier: 31 days overdue; | High | 10018
PSIL-PR-2026-0014 | 2026-07-10 | Cutting | Cutting Manager | Toe Puff & Counter Sheet | Synthetic & Textile | Thermoplastic 1.2 mm | OPEX | OPX-2026-114 | 2026-07-11 | Approved | GM Operations | Dongguan Sole Tech Co. | Import | PSIL-PO-2026-0014 | 2026-07-16 | 3700 | sheet | 3.35 | USD | 122 | 418.36 | 1512190 | 408.7 |  |  | -35742 | -2.309% | 15% | 1739018.5 | LC at Sight |  |  | 1739018.5 | 1739018.5 | 100% | 0 | 0 | Fully Paid | 2026-08-21 |  |  |  | 2026-08-31 | 2026-08-27 | 3700 | 100% | 0 | 0 | All In-house | 2026-08-29 | 1 | 5 | 44 | 50 | 0 | OTIF | Approved | Photos\PSIL-PR-2026-0014.jpg |  | Closed | OK |  |  |  | Price above budget — CFO note on file
PSIL-PR-2026-0015 | 2026-07-14 | Finishing & Packing | Finishing Manager | Shoe Box – Printed | Packaging | Kraft, 3-ply, branded | OPEX | OPX-2026-115 | 2026-07-16 | Approved | CFO | Chattogram Packaging Ltd | Local | PSIL-PO-2026-0015 | 2026-07-20 | 17300 | pcs | 39.22 | BDT | 1 | 38.66 | 678506 | 39.22 |  |  | 9688 | 1.449% | 5% | 712431.3 | Credit 30 Days |  |  | 712431.3 | 712431.3 | 100% | 0 | 0 | Fully Paid | 2026-09-09 |  |  |  | 2026-08-10 | 2026-08-07 | 17300 | 100% | 0 | 0 | All In-house | 2026-08-10 | 2 | 4 | 21 | 27 | 0 | OTIF | Approved | Photos\PSIL-PR-2026-0015.jpg |  | Closed | OK
PSIL-PR-2026-0016 | 2026-07-17 | Finishing & Packing | Finishing Manager | Export Carton – 5 Ply | Packaging | 12 pair master | OPEX | OPX-2026-116 | 2026-07-20 | Approved | GM Operations | Chattogram Packaging Ltd | Local | PSIL-PO-2026-0016 | 2026-07-23 | 1500 | pcs | 141 | BDT | 1 | 145.91 | 211500 | 141 |  |  | -7365 | -3.365% | 5% | 222075 | 30% Advance / 70% after In-house | 66622.5 |  | 155452.5 | 222075 | 100% | 0 | 0 | Fully Paid | 2026-08-19 |  |  |  | 2026-08-07 | 2026-08-04 | 1500 | 100% | 0 | 0 | All In-house | 2026-08-04 | 3 | 3 | 12 | 18 | 0 | OTIF | Approved | Photos\PSIL-PR-2026-0016.jpg |  | Closed | OK
PSIL-PR-2026-0017 | 2026-07-21 | Maintenance | Maintenance Manager | Sewing Machine Needles & Spares | Spare Parts | Post-bed, assorted | OPEX | OPX-2026-117 | 2026-07-22 | Approved | CFO | Dhaka Spares & Tools | Local | PSIL-PO-2026-0017 | 2026-07-26 | 40 | set | 1872 | BDT | 1 | 1866.98 | 74880 | 1872 |  |  | 200.8 | 0.2689% | 7.5% | 80496 | Credit 30 Days |  | 40248 |  | 40248 | 50% | 40248 | 0 | Partially Paid | 2026-09-20 | 2026-09-20 | 25 | 1-30 Days | 2026-08-17 | 2026-08-20 | 40 | 100% | 0 | 0 | All In-house | 2026-08-21 | 1 | 4 | 26 | 31 | 4 | Not OTIF | Rejected |  |  | In-house Closed - Payment Due | OK | Pay supplier: 25 days overdue; QC rejected: return / replace; | High | 10022
PSIL-PR-2026-0018 | 2026-07-23 | Compliance & HSE | HSE Officer | Safety PPE (Masks, Gloves, Goggles) | Safety & Facility | Chemical area kit | OPEX | OPX-2026-118 | 2026-07-25 | Approved | CFO | Dhaka Spares & Tools | Local | PSIL-PO-2026-0018 | 2026-07-27 | 200 | set | 999 | BDT | 1 | 926.34 | 199800 | 999 |  |  | 14532 | 7.844% | 7.5% | 214785 | Credit 30 Days |  | 107392.5 |  | 107392.5 | 50% | 107392.5 | 0 | Partially Paid | 2026-09-09 | 2026-09-09 | 36 | 31-60 Days | 2026-08-06 | 2026-08-09 | 200 | 100% | 0 | 0 | All In-house | 2026-08-10 | 2 | 2 | 14 | 18 | 4 | Not OTIF | Approved with Deviation |  |  | In-house Closed - Payment Due | OK | Pay supplier: 36 days overdue; | High | 10023
PSIL-PR-2026-0019 | 2026-07-27 | Maintenance | Maintenance Manager | Computerised Post-bed Sewing Machine | Machinery & Equipment | Single needle, servo | CAPEX | CPX-2026-119 | 2026-08-01 | Approved | MD | Jiangsu Footwear Machinery Co. | Import | PSIL-PO-2026-0019 | 2026-08-06 | 16 | unit | 2543.07 | USD | 122 | 313877.28 | 4964072.64 | 310254.54 |  |  | -57963.84 | -1.154% | 12% | 5559761.3568 | 50% Advance / 50% after Installation | 2779880.68 |  |  | 2779880.68 | 50% | 2779880.68 | 0 | Initial / Advance Paid | 2026-08-09 | 2026-11-01 | 0 | Not Yet Due | 2026-10-03 | 2026-09-29 | 15 | 93.75% | 1 | 347485.0848 | Short Closed - 1 unit not received | 2026-10-02 | 5 | 5 | 57 | 67 | 0 | Not OTIF | Approved with Deviation |  |  | In-house Closed - Payment Due | OK | Short closed: claim balance / credit note; | Medium | 20024
PSIL-PR-2026-0020 | 2026-07-29 | Maintenance | Maintenance Manager | Leather Skiving Machine | Machinery & Equipment | Bell-knife type | CAPEX | CPX-2026-120 | 2026-08-05 | Approved | MD | Jiangsu Footwear Machinery Co. | Import | PSIL-PO-2026-0020 | 2026-08-08 | 3 | unit | 3837.39 | USD | 122 | 468392.92 | 1404484.74 | 468161.58 |  |  | -694.02 | -0.04939% | 12% | 1573022.9088 | 50% Advance / 50% after Installation | 786511.45 |  |  | 786511.45 | 50% | 786511.46 | 0 | Initial / Advance Paid | 2026-08-11 | 2026-10-30 | 0 | Not Yet Due | 2026-09-29 | 2026-09-29 | 3 | 100% | 0 | 0 | All In-house | 2026-09-30 | 7 | 3 | 53 | 63 | 1 | Not OTIF | Approved |  |  | In-house Closed - Payment Due | OK
PSIL-PR-2026-0021 | 2026-08-01 | Maintenance | Maintenance Manager | Hydraulic Sole Pressing Machine | Machinery & Equipment | Twin station | CAPEX | CPX-2026-121 | 2026-08-09 | Approved | MD | Jiangsu Footwear Machinery Co. | Import | PSIL-PO-2026-0021 | 2026-08-14 | 3 | unit | 53430.12 | CNY | 17 | 905443.9 | 2724936.12 | 908312.04 |  |  | 8604.42 | 0.3168% | 12% | 3051928.4544 | 50% Advance / 50% after Installation | 1525964.23 |  |  | 1525964.23 | 50% | 1525964.22 | 0 | Initial / Advance Paid | 2026-08-17 | 2026-10-31 | 0 | Not Yet Due | 2026-09-22 | 2026-09-30 | 3 | 100% | 0 | 0 | All In-house | 2026-10-01 | 8 | 5 | 48 | 61 | 9 | Not OTIF | Approved |  |  | In-house Closed - Payment Due | OK
PSIL-PR-2026-0022 | 2026-08-04 | Maintenance | Maintenance Manager | Screw Air Compressor 30 HP | Machinery & Equipment | With dryer & tank | CAPEX | CPX-2026-122 | 2026-08-10 | Approved | MD | Dhaka Spares & Tools | Local | PSIL-PO-2026-0022 | 2026-08-12 | 1 | unit | 1495361 | BDT | 1 | 1474015.39 | 1495361 | 1495361 |  |  | 21345.61 | 1.448% | 7.5% | 1607513.075 | 50% Advance / 50% after Installation | 803756.54 |  | 803756.54 | 1607513.08 | 100% | 0 | 0 | Fully Paid | 2026-09-26 |  |  |  | 2026-08-24 | 2026-08-27 | 1 | 100% | 0 | 0 | All In-house | 2026-08-27 | 6 | 2 | 15 | 23 | 3 | Not OTIF | Approved |  |  | Closed | OK
PSIL-PR-2026-0023 | 2026-08-09 | IT | IT Manager | Laptop for PPC & Costing Team | IT Equipment | i7, 16 GB, 512 GB SSD | CAPEX | CPX-2026-123 | 2026-08-14 | Approved | MD | Tech Point BD | Local | PSIL-PO-2026-0023 | 2026-08-16 | 7 | unit | 103649 | BDT | 1 | 95683.92 | 725543 | 103649 |  |  | 55755.56 | 8.324% | 5% | 761820.15 | 50% Advance / 50% after Installation | 380910.08 |  |  | 380910.08 | 50% | 380910.07 | 0 | Initial / Advance Paid | 2026-08-19 | 2026-09-26 | 19 | 1-30 Days | 2026-08-29 | 2026-08-27 | 7 | 100% | 0 | 0 | All In-house | 2026-08-27 | 5 | 2 | 11 | 18 | 0 | OTIF | Approved |  |  | In-house Closed - Payment Due | OK | Pay supplier: 19 days overdue; | Medium | 20028 | Price above budget — CFO note on file
PSIL-PR-2026-0024 | 2026-08-11 | Cutting | Cutting Manager | Pig Lining Leather | Leather & Upper | 0.8 mm, Natural | OPEX | OPX-2026-124 | 2026-08-13 | Approved | GM Operations | Savar Leather Works Ltd | Local | PSIL-PO-2026-0024 | 2026-08-17 | 11300 | sqft | 98.03 | BDT | 1 | 95.03 | 1107739 | 98.03 | 97 | 1.062% | 33900 | 3.157% | 5% | 1163125.95 | 30% Advance / 70% after In-house | 348937.78 |  |  | 348937.78 | 30% | 814188.17 | 0 | Initial / Advance Paid | 2026-08-19 | 2026-09-23 | 22 | 1-30 Days | 2026-09-04 | 2026-09-07 | 11300 | 100% | 0 | 0 | All In-house | 2026-09-08 | 2 | 4 | 22 | 28 | 4 | Not OTIF | Rejected |  |  | In-house Closed - Payment Due | OK | Pay supplier: 22 days overdue; QC rejected: return / replace; | High | 10029
PSIL-PR-2026-0025 | 2026-08-13 | Compliance & HSE | HSE Officer | Safety PPE (Masks, Gloves, Goggles) | Safety & Facility | Chemical area kit | OPEX | OPX-2026-125 | 2026-08-17 | Approved | GM Operations | Dhaka Spares & Tools | Local | PSIL-PO-2026-0025 | 2026-08-18 | 200 | set | 913 | BDT | 1 | 928.43 | 182600 | 913 | 999 | -8.609% | -3086 | -1.662% | 7.5% | 196295 | Credit 30 Days |  |  | 196295 | 196295 | 100% | 0 | 0 | Fully Paid | 2026-10-07 |  |  |  | 2026-09-07 | 2026-09-07 | 200 | 100% | 0 | 0 | All In-house | 2026-09-07 | 4 | 1 | 20 | 25 | 0 | OTIF | Approved with Deviation |  |  | Closed | OK
PSIL-PR-2026-0026 | 2026-08-16 | Stitching | Stitching Manager | Waxed Cotton Laces | Trims & Accessories | 120 cm, Brown | OPEX | OPX-2026-126 | 2026-08-18 | Approved | CFO | Delta Thread & Trims | Local | PSIL-PO-2026-0026 | 2026-08-22 | 14100 | pair | 15.01 | BDT | 1 | 14.39 | 211641 | 15.01 | 15.15 | -0.9241% | 8742 | 4.309% | 5% | 222223.05 | 100% Advance | 222223.05 |  |  | 222223.05 | 100% | 0 | 0 | Fully Paid | 2026-08-23 |  |  |  | 2026-09-15 | 2026-09-11 | 14100 | 100% | 0 | 0 | All In-house | 2026-09-12 | 2 | 4 | 21 | 27 | 0 | OTIF | Approved | Photos\PSIL-PR-2026-0026.jpg |  | Closed | OK
PSIL-PR-2026-0027 | 2026-08-20 | Maintenance | Maintenance Manager | Sewing Machine Needles & Spares | Spare Parts | Post-bed, assorted | OPEX | OPX-2026-127 | 2026-08-21 | Approved | GM Operations | Dhaka Spares & Tools | Local | PSIL-PO-2026-0027 | 2026-08-22 | 83 | set | 1856 | BDT | 1 | 1834.08 | 154048 | 1856 | 1872 | -0.8547% | 1819.36 | 1.195% | 7.5% | 165601.6 | 30% Advance / 70% after In-house | 49680.48 |  | 115921.12 | 165601.6 | 100% | 0 | 0 | Fully Paid | 2026-09-27 |  |  |  | 2026-09-06 | 2026-09-09 | 83 | 100% | 0 | 0 | All In-house | 2026-09-12 | 1 | 1 | 21 | 23 | 6 | Not OTIF | Approved |  |  | Closed | OK
PSIL-PR-2026-0028 | 2026-08-22 | Maintenance | Maintenance Manager | Sewing Machine Needles & Spares | Spare Parts | Post-bed, assorted | OPEX | OPX-2026-128 | 2026-08-25 | Rejected | CFO | Dhaka Spares & Tools | Local |  |  | 54 | set | 2012 | BDT | 1 | 1882.01 | 108648 | 2012 |  |  | 7019.46 | 6.907% | 7.5% | 116796.6 |  |  |  |  | 0 | 0% | 116796.6 |  | No PO Yet |  |  |  | No Due Date |  |  |  | 0% |  |  | No PO Yet |  | 3 | [8 empty] | Rejected | OK
PSIL-PR-2026-0029 | 2026-08-25 | Cutting | Cutting Manager | PU Synthetic Leather | Synthetic & Textile | 1.0 mm, White, 54" | OPEX | OPX-2026-129 | 2026-08-27 | Approved | GM Operations | Dongguan Sole Tech Co. | Import | PSIL-PO-2026-0029 | 2026-08-29 | 5200 | meter | 3.04 | USD | 122 | 387.41 | 1928576 | 370.88 | 379.42 | -2.251% | -85956 | -4.267% | 15% | 2217862.4 | LC at Sight |  |  | 2217862.4 | 2217862.4 | 100% | 0 | 2217862 | Fully Paid | 2026-10-06 |  |  |  | 2026-10-16 |  |  | 0% | 5200 | 2217862.4 | Not Started - 5,200 meter pending |  | 2 | 2 |  |  | 0 |  |  |  |  | PO Issued - Awaiting Delivery | OK
PSIL-PR-2026-0030 | 2026-08-30 | Compliance & HSE | HSE Officer | Safety PPE (Masks, Gloves, Goggles) | Safety & Facility | Chemical area kit | OPEX | OPX-2026-130 | 2026-09-02 | Approved | CFO | Dhaka Spares & Tools | Local | PSIL-PO-2026-0030 | 2026-09-04 | 200 | set | 963 | BDT | 1 | 940.14 | 192600 | 963 | 913 | 5.476% | 4572 | 2.432% | 7.5% | 207045 | 30% Advance / 70% after In-house | 62113.5 |  |  | 62113.5 | 30% | 144931.5 | 0 | Initial / Advance Paid | 2026-09-06 | 2026-10-03 | 12 | 1-30 Days | 2026-09-20 | 2026-09-18 | 200 | 100% | 0 | 0 | All In-house | 2026-09-18 | 3 | 2 | 14 | 19 | 0 | OTIF | Approved |  |  | In-house Closed - Payment Due | OK | Pay supplier: 12 days overdue; | Medium | 20035
PSIL-PR-2026-0031 | 2026-08-31 | Lasting & Assembly | Lasting Manager | PU Adhesive (Solvent Based) | Chemicals & Adhesives | 15 kg drum | OPEX | OPX-2026-131 | 2026-09-03 | Approved | GM Operations | Gazipur Chem Trade | Local | PSIL-PO-2026-0031 | 2026-09-06 | 1300 | kg | 438 | BDT | 1 | 408.86 | 569400 | 438 | 431 | 1.624% | 37882 | 7.127% | 7.5% | 612105 | Credit 30 Days |  |  |  | 0 | 0% | 612105 | 0 | Not Paid |  | 2026-10-20 | 0 | Not Yet Due | 2026-09-25 | 2026-09-19 | 1266 | 97.38% | 34 | 16008.9 | Short Closed - 34 kg not received | 2026-09-20 | 3 | 3 | 14 | 20 | 0 | Not OTIF | Approved | Photos\PSIL-PR-2026-0031.jpg |  | In-house Closed - Payment Due | OK | Short closed: claim balance / credit note; | Medium | 20036
PSIL-PR-2026-0032 | 2026-09-03 | Lasting & Assembly | Lasting Manager | TPR Outsole – Ladies Casual | Sole & Bottom | Size 35–41, Beige | OPEX | OPX-2026-132 | 2026-09-05 | Approved | GM Operations | Bengal Sole Industries | Local | PSIL-PO-2026-0032 | 2026-09-09 | 6600 | pair | 124 | BDT | 1 | 120.22 | 818400 | 124 | 125 | -0.8% | 24948 | 3.144% | 5% | 859320 | Credit 30 Days |  |  |  | 0 | 0% | 859320 | 0 | Not Paid |  | 2026-10-27 | 0 | Not Yet Due | 2026-09-27 | 2026-09-25 | 6433 | 97.47% | 167 | 21743.4 | Short Closed - 167 pair not received | 2026-09-27 | 2 | 4 | 18 | 24 | 0 | Not OTIF | Approved | Photos\PSIL-PR-2026-0032.jpg |  | In-house Closed - Payment Due | OK | Short closed: claim balance / credit note; | Medium | 20037 | Price above budget — CFO note on file
PSIL-PR-2026-0033 | 2026-09-08 | Cutting | Cutting Manager | Cow Nappa Upper Leather | Leather & Upper | 1.2–1.4 mm, Black | OPEX | OPX-2026-133 | 2026-09-12 | Approved | CFO | Savar Leather Works Ltd | Local | PSIL-PO-2026-0033 | 2026-09-16 | 16300 | sqft | 2.4 | USD | 122 | 281.36 | 4772640 | 292.8 | 286.7 | 2.128% | 186472 | 4.066% | 5% | 5011272 | 100% Advance | 5011272 |  |  | 5011272 | 100% | 0 | 281308 | Fully Paid | 2026-09-17 |  |  |  | 2026-09-27 | 2026-09-30 | 15385 | 94.39% | 915 | 281307.6 | Short Closed - 915 sqft not received | 2026-10-03 | 4 | 4 | 17 | 25 | 6 | Not OTIF | Approved | Photos\PSIL-PR-2026-0033.jpg |  | Closed | OK | Short closed: claim balance / credit note BDT 281,308; | High | 10038
PSIL-PR-2026-0034 | 2026-09-10 | Lasting & Assembly | Lasting Manager | PU Adhesive (Solvent Based) | Chemicals & Adhesives | 15 kg drum | OPEX | OPX-2026-134 | 2026-09-12 | Approved | GM Operations | Gazipur Chem Trade | Local | PSIL-PO-2026-0034 | 2026-09-15 | 1200 | kg | 437 | BDT | 1 | 415.09 | 524400 | 437 | 438 | -0.2283% | 26292 | 5.278% | 7.5% | 563730 | Credit 30 Days |  |  |  | 0 | 0% | 563730 | 0 | Not Paid |  | 2026-10-19 | 0 | Not Yet Due | 2026-09-25 | 2026-09-19 | 1200 | 100% | 0 | 0 | All In-house | 2026-09-19 | 2 | 3 | 4 | 9 | 0 | OTIF | Rejected |  |  | In-house Closed - Payment Due | OK | QC rejected: return / replace; | High | 10039
PSIL-PR-2026-0035 | 2026-09-12 | Lasting & Assembly | Lasting Manager | TPR Outsole – Ladies Casual | Sole & Bottom | Size 35–41, Beige | OPEX | OPX-2026-135 | 2026-09-15 | Approved | CFO | Bengal Sole Industries | Local | PSIL-PO-2026-0035 | 2026-09-18 | 4700 | pair | 125 | BDT | 1 | 119.14 | 587500 | 125 | 124 | 0.8065% | 27542 | 4.919% | 5% | 616875 | 100% Advance | 616875 |  |  | 616875 | 100% | 0 | 0 | Fully Paid | 2026-09-19 |  |  |  | 2026-09-28 | 2026-09-24 | 4700 | 100% | 0 | 0 | All In-house | 2026-09-25 | 3 | 3 | 7 | 13 | 0 | OTIF | Approved | Photos\PSIL-PR-2026-0035.jpg |  | Closed | OK
PSIL-PR-2026-0036 | 2026-09-16 | Stitching | Stitching Manager | Waxed Cotton Laces | Trims & Accessories | 120 cm, Brown | OPEX | OPX-2026-136 | 2026-09-19 | Approved | CFO | Delta Thread & Trims | Local | PSIL-PO-2026-0036 | 2026-09-22 | 19000 | pair | 13.84 | BDT | 1 | 13.61 | 262960 | 13.84 | 15.01 | -7.795% | 4370 | 1.69% | 5% | 276108 | 30% Advance / 70% after In-house | 82832.4 |  |  | 82832.4 | 30% | 193275.6 | 0 | Initial / Advance Paid | 2026-09-24 | 2026-10-21 | 0 | Not Yet Due | 2026-10-04 | 2026-10-03 | 19000 | 100% | 0 | 0 | All In-house | 2026-10-06 | 3 | 3 | 14 | 20 | 2 | Not OTIF | Approved | Photos\PSIL-PR-2026-0036.jpg |  | In-house Closed - Payment Due | OK
PSIL-PR-2026-0037 | 2026-09-18 | Lasting & Assembly | Lasting Manager | EVA Midsole Sheet | Sole & Bottom | 6 mm, Shore 45A | OPEX | OPX-2026-137 | 2026-09-19 | Approved | CFO | Dongguan Sole Tech Co. | Import | PSIL-PO-2026-0037 | 2026-09-23 | 4100 | sheet | 10.04 | CNY | 17 | 157.54 | 699788 | 170.68 | 171.7 | -0.5941% | 53874 | 8.341% | 15% | 804756.2 | LC at Sight |  |  |  | 0 | 0% | 804756.2 | 0 | Not Paid |  | 2026-11-05 | 0 | Not Yet Due | 2026-11-15 |  |  | 0% | 4100 | 804756.2 | Not Started - 4,100 sheet pending |  | 1 | 4 |  |  | 0 |  |  |  |  | PO Issued - Awaiting Delivery | OK
PSIL-PR-2026-0038 | 2026-09-21 | Cutting | Cutting Manager | Cellulose Insole Board | Synthetic & Textile | 2.0 mm, 1x1.5 m | OPEX | OPX-2026-138 | 2026-09-23 | Approved | GM Operations | Narayanganj Board Mills | Local | PSIL-PO-2026-0038 | 2026-09-26 | 1600 | sheet | 335 | BDT | 1 | 334.55 | 536000 | 335 | 336 | -0.2976% | 720 | 0.1345% | 5% | 562800 | 100% Advance | 562800 |  |  | 562800 | 100% | 0 | 190297 | Fully Paid | 2026-09-27 |  |  |  | 2026-10-17 | 2026-10-13 | 1059 | 66.19% | 541 | 190296.75 | Pending 541 sheet (66% received) |  | 2 | 3 |  |  | 0 |  | Pending |  |  | Receiving In-house | OK
PSIL-PR-2026-0039 | 2026-09-24 | Lasting & Assembly | Lasting Manager | Rubber Outsole – Men's Derby | Sole & Bottom | Size 39–45, Black | OPEX | OPX-2026-139 |  | Pending |  | Bengal Sole Industries | Local |  |  | 11800 | pair | 197 | BDT | 1 | 189.35 | 2324600 | 197 |  |  | 90270 | 4.04% | 5% | 2440830 |  |  |  |  | 0 | 0% | 2440830 |  | No PO Yet |  |  |  | No Due Date |  |  |  | 0% |  |  | No PO Yet | [10 empty] | Awaiting Approval | OK | Get approval: PR waiting 21 days; | Medium | 20044
PSIL-PR-2026-0040 | 2026-09-29 | Cutting | Cutting Manager | Toe Puff & Counter Sheet | Synthetic & Textile | Thermoplastic 1.2 mm | OPEX | OPX-2026-140 | 2026-09-30 | Approved | CFO | Dongguan Sole Tech Co. | Import | PSIL-PO-2026-0040 | 2026-10-01 | 3600 | sheet | 3.27 | USD | 122 | 415.39 | 1436184 | 398.94 | 408.7 | -2.388% | -59220 | -3.96% | 15% | 1651611.6 | LC at Sight |  |  |  | 0 | 0% | 1651611.6 | 0 | Not Paid |  | 2026-10-26 | 0 | Not Yet Due | 2026-11-05 |  |  | 0% | 3600 | 1651611.6 | Not Started - 3,600 sheet pending |  | 1 | 1 |  |  | 0 |  |  |  |  | PO Issued - Awaiting Delivery | OK
PSIL-PR-2026-0041 | 2026-10-02 | Lasting & Assembly | Lasting Manager | Rubber Outsole – Men's Derby | Sole & Bottom | Size 39–45, Black | OPEX | OPX-2026-141 | 2026-10-06 | Approved | CFO | Bengal Sole Industries | Local |  |  | 8000 | pair | 201 | BDT | 1 | 183.63 | 1608000 | 201 |  |  | 138960 | 9.459% | 5% | 1688400 |  |  |  |  | 0 | 0% | 1688400 |  | No PO Yet |  |  |  | No Due Date |  |  |  | 0% |  |  | No PO Yet |  | 4 | [8 empty] | Approved - PO Pending | OK | Issue PO: approved 9 days ago; Negotiate price: 9% above budget; | Medium | 20046
PSIL-PR-2026-0042 | 2026-10-05 | Cutting | Cutting Manager | Cow Nappa Upper Leather | Leather & Upper | 1.2–1.4 mm, Black | OPEX | OPX-2026-142 | 2026-10-06 | Approved | GM Operations | Savar Leather Works Ltd | Local | PSIL-PO-2026-0042 | 2026-10-07 | 16700 | sqft | 2.45 | USD | 122 | 286.52 | 4991630 | 298.9 | 292.8 | 2.083% | 206746 | 4.321% | 5% | 5241211.5 | 30% Advance / 70% after In-house | 1572363.45 |  |  | 1572363.45 | 30% | 3668848.05 | 1572363 | Initial / Advance Paid | 2026-10-09 | 2026-11-12 | 0 | Not Yet Due | 2026-10-28 |  |  | 0% | 16700 | 5241211.5 | Not Started - 16,700 sqft pending |  | 1 | 1 |  |  | 0 |  |  |  |  | PO Issued - Awaiting Delivery | OK
PSIL-PR-2026-0043 | 2026-10-08 | Cutting | Cutting Manager | Pig Lining Leather | Leather & Upper | 0.8 mm, Natural | OPEX | OPX-2026-143 | 2026-10-11 | Approved | CFO | Savar Leather Works Ltd | Local |  |  | 14600 | sqft | 90.24 | BDT | 1 | 96.35 | 1317504 | 90.24 |  |  | -89206 | -6.341% | 5% | 1383379.2 |  |  |  |  | 0 | 0% | 1383379.2 |  | No PO Yet |  |  |  | No Due Date |  |  |  | 0% |  |  | No PO Yet |  | 3 | [8 empty] | Approved - PO Pending | OK | Issue PO: approved 4 days ago; | Low | 30048
PSIL-PR-2026-0044 | 2026-10-09 | Lasting & Assembly | Lasting Manager | Primer & Halogenating Agent | Chemicals & Adhesives | Rubber sole primer | OPEX | OPX-2026-144 |  | Pending |  | Gazipur Chem Trade | Local |  |  | 500 | kg | 507 | BDT | 1 | 524.68 | 253500 | 507 |  |  | -8840 | -3.37% | 7.5% | 272512.5 |  |  |  |  | 0 | 0% | 272512.5 |  | No PO Yet |  |  |  | No Due Date |  |  |  | 0% |  |  | No PO Yet | [10 empty] | Awaiting Approval | OK | Get approval: PR waiting 6 days; | Low | 30049
PSIL-PR-2026-0045 | 2026-10-12 |  |  | Heel Counter Stiffener (demo: incomplete entry) | [29 empty] | 0 |  |  |  | No PO Yet | [10 empty] | No PO Yet | [10 empty] | Awaiting Approval | PR info missing; | Fix data entry (see Data Check); | Low | 30050 | Demo line — orange cells show what is still required
Note on Y5: Unit price (BDT) on the most recent earlier PO for the same Item name. Keep item names identical so price history links up.
Note on Z5: Positive = this PO is dearer than the last time we bought the same item. Red when above the price alert threshold (Settings).
Note on AA5: Positive = paid more than budget/standard price (unfavourable). Negative = saving.
Note on AL5: Money paid for goods not yet received (advance exposure). On short-closed lines this is the amount to recover from the supplier.
Note on AM5: Automatic: No PO Yet → Not Paid → Initial / Advance Paid → Partially Paid → Fully Paid.
Note on AQ5: Ages the outstanding payable against Next Payment Due Date and Settings report date.
Note on BE5: On-Time In-Full: closed on/before committed date AND received ≥ OTIF tolerance (Settings).
Note on BG5: Path or SharePoint / Google Drive link to the approved-sample photo or signed swatch card.
Note on BH5: Paste the approved-sample photo here: Excel 365 → Insert ▸ Pictures ▸ Place in Cell (stays with the row when filtering/sorting). Sample swatches shown are placeholders.
Note on BI5: Automatic lifecycle stage driven by approval, PO, in-house and payment fields.
Note on BK5: Automatic to-do: overdue payment, late delivery, approval or PO beyond SLA, price above budget before PO, short closed, QC rejected, advance at risk, data errors. Listed on Action_Tracker.
Note on BL5: High: payment >30 days overdue, open delivery >15 days late, QC rejected, money at risk. Medium: other overdue/late (>7 days) or short closed. Low: everything else.

## Supplier_Scorecard
Supplier Scorecard, Performance Rating & Spend Concentration
Score (0–100) = 40% OTIF + 20% In-Full + 25% QC acceptance + 15% price discipline (no above-budget variance = full marks; ≥10% over budget = zero). A ≥ 80 · B 60–79 · C < 60.
Supplier | POs | Spend incl. Tax (BDT) | Share of Spend | Paid (BDT) | Outstanding (BDT) | Closed Deliveries | OTIF % | In-Full % | Avg Lead Time (days) | Avg Delay (days) | Late Open POs | Short-Closed Lines | Pending In-house (BDT) | QC Acceptance % | Avg Price Variance % | Score | Rating | Sort key
Savar Leather Works Ltd | 6 | 17829948.15 | 31.55% | 11963532.73 | 5866415.42 | 5 | 60% | 80% | 15.6 | 2 | 0 | 1 | 5241211.5 | 60% | 2.685% | 66 | B — Approved | 17829948.151
Bengal Sole Industries | 4 | 8646225 | 15.3% | 2583525 | 6062700 | 4 | 50% | 50% | 12.5 | 0 | 0 | 2 | 0 | 100% | 4.172% | 64 | B — Approved | 8646225.001
Gazipur Chem Trade | 4 | 2383920 | 4.218% | 935572.5 | 1448347.5 | 4 | 50% | 50% | 13.25 | 2.5 | 0 | 2 | 0 | 50% | 4.494% | 51 | C — Review | 2383920.001
Chattogram Packaging Ltd | 2 | 934506.3 | 1.653% | 934506.3 | 0 | 2 | 100% | 100% | 16.5 | 0 | 0 | 0 | 0 | 100% | -0.9583% | 100 | A — Preferred | 934506.301
Delta Thread & Trims | 5 | 1331038.8 | 2.355% | 728620.2 | 602418.6 | 5 | 40% | 80% | 16.8 | 1.2 | 0 | 1 | 0 | 80% | 1.642% | 65 | B — Approved | 1331038.801
Narayanganj Board Mills | 2 | 1268400 | 2.244% | 915600 | 352800 | 1 | 0% | 100% | 31 | 8 | 0 | 0 | 190296.75 | 100% | 0.5571% | 59 | C — Review | 1268400.001
Dongguan Sole Tech Co. | 6 | 10589896.9 | 18.74% | 8133529.1 | 2456367.8 | 3 | 100% | 100% | 44 | 0 | 0 | 0 | 4674230.2 | 100% | 1.162% | 98 | A — Preferred | 10589896.901
Jiangsu Footwear Machinery Co. | 3 | 10184712.72 | 18.02% | 5092356.36 | 5092356.36 | 3 | 0% | 66.67% | 52.6667 | 3.3333 | 0 | 1 | 0 | 100% | -0.2956% | 53 | C — Review | 10184712.721
Dhaka Spares & Tools | 6 | 2588532.275 | 4.58% | 2179163.68 | 409368.6 | 6 | 33.33% | 100% | 18.3333 | 2.8333 | 0 | 0 | 0 | 83.33% | 2.633% | 65 | B — Approved | 2588532.276
Tech Point BD | 1 | 761820.15 | 1.348% | 380910.08 | 380910.07 | 1 | 100% | 100% | 11 | 0 | 0 | 0 | 0 | 100% | 8.324% | 88 | A — Preferred | 761820.151
-15
-16
-17
-18
-19
-20
-21
-22
-23
-24
-25
-26
-27
-28
-29
-30
-31
-32
-33
-34
TOTAL / OVERALL | 39 | 56519000.295 | 100% | 33847315.95 | 22671684.35 | 34 | 50% | 79.41% | 21.7647 | 1.7941 | 0 | 7 | 10105738.45 | 82.35% | 2.421% | 71 | 3 A · 4 B · 3 C
SPEND CONCENTRATION — one supplier above 30% of spend is a supply-continuity risk worth a second source.
Largest supplier |  | Savar Leather Works Ltd
Largest supplier share |  | 31.55%
Herfindahl index (HHI, 0–10,000) |  | 1959
Concentration reading |  | Moderately concentrated

## Spend_Analysis
Spend Analysis — ABC / Pareto, Savings, Payment Terms & Sourcing Mix
Categories ranked by spend (largest first). ABC: A = categories making up the first 80% of spend, B = next 15%, C = the rest (cut-offs in Settings).
| Savings vs budget price |  | Overspend vs budget price |  | Net price variance |  | A-class categories |  | Items dearer than last PO
| 373468.86 |  | 1341825.21 |  | 968356.35 |  | 4 of 10 |  | 6 lines (avg +2.2%)
Rank | Category | PO Lines | Spend incl. Tax (BDT) | Spend (BDT Lakh) | Share of Spend | Cumulative Share | ABC Class | Avg Price Variance % | Savings vs Budget (BDT) | Overspend vs Budget (BDT) | Pending In-house (BDT)
1 | Leather & Upper | 6 | 17829948.15 | 178.2995 | 31.55% | 31.55% | A | 2.685% | 89206 | 602963 | 5241211.5 | 1 | Leather & Upper | 17829948.15 | 17829948.151
2 | Machinery & Equipment | 4 | 11792225.795 | 117.9223 | 20.86% | 52.41% | A | 0.1403% | 58657.86 | 29950.03 | 0 | 8 | Synthetic & Textile | 10105756.7 | 10105756.701
3 | Sole & Bottom | 6 | 10398765.2 | 103.9877 | 18.4% | 70.81% | A | 5.135% | 2310 | 423962 | 804756.2 | 3 | Sole & Bottom | 10398765.2 | 10398765.201
4 | Synthetic & Textile | 6 | 10105756.7 | 101.0576 | 17.88% | 88.69% | A | -1.328% | 180918 | 47496 | 4059770.75 | 2 | Chemicals & Adhesives | 2383920 | 2383920.001
5 | Chemicals & Adhesives | 4 | 2383920 | 23.8392 | 4.218% | 92.91% | B | 4.494% | 8840 | 118245 | 0 | 4 | Trims & Accessories | 1331038.8 | 1331038.801
6 | Trims & Accessories | 5 | 1331038.8 | 13.3104 | 2.355% | 95.26% | B | 1.642% | 23086 | 25622 | 0 | 5 | Packaging | 934506.3 | 934506.301
7 | Packaging | 2 | 934506.3 | 9.3451 | 1.653% | 96.92% | C | -0.9583% | 7365 | 9688 | 0 | 6 | Spare Parts | 362894.2 | 362894.201
8 | IT Equipment | 1 | 761820.15 | 7.6182 | 1.348% | 98.26% | C | 8.324% | 0 | 55755.56 | 0 | 9 | Machinery & Equipment | 11792225.795 | 11792225.796
9 | Safety & Facility | 3 | 618125 | 6.1813 | 1.094% | 99.36% | C | 2.871% | 3086 | 19104 | 0 | 10 | IT Equipment | 761820.15 | 761820.151
10 | Spare Parts | 2 | 362894.2 | 3.6289 | 0.6421% | 100% | C | 2.79% | 0 | 9039.62 | 0 | 7 | Safety & Facility | 618125 | 618125.001
11 | [11 empty] | 11 |  | 0 | -16
12 | [11 empty] | 12 |  | 0 | -17
13 | [11 empty] | 13 |  | 0 | -18
14 | [11 empty] | 14 |  | 0 | -19
15 | [11 empty] | 15 |  | 0 | -20
16 | [11 empty] | 16 |  | 0 | -21
17 | [11 empty] | 17 |  | 0 | -22
18 | [11 empty] | 18 |  | 0 | -23
19 | [11 empty] | 19 |  | 0 | -24
20 | [11 empty] | 20 |  | 0 | -25
| TOTAL | 39 | 56519000.295 | 565.19 | 100% |  |  | 2.421% | 373468.86 | 1341825.21 | 10105738.45
PAYMENT TERMS MIX — working-capital view (advance terms tie up cash before goods arrive)
# | Payment Terms | PO Lines | PO Value (BDT) | Share of Value | Paid (BDT) | Outstanding (BDT) | Paid Ahead of Receipt (BDT)
1 | 100% Advance | 7 | 8829879.55 | 17.44% | 8829879.55 | 0 | 488285
2 | 30% Advance / 70% after In-house | 8 | 10865274.55 | 21.47% | 5743563.23 | 5121711.32 | 1572363
3 | Credit 30 Days | 13 | 7777985.05 | 15.37% | 4059564.55 | 3718420.5 | 0
4 | Credit 60 Days | 0 | 0 | 0% | 0 | 0 | 0
5 | LC at Sight | 6 | 10589896.9 | 20.92% | 8133529.1 | 2456367.8 | 2217862
6 | 50% Advance / 50% after Installation | 5 | 12554045.945 | 24.8% | 7080779.52 | 5473266.43 | 0
7
8
9
10
SOURCING MIX — Local vs Import
# | Origin | PO Lines | PO Value (BDT) | Share of Value | Avg Lead Time (days) | OTIF % | Pending In-house (BDT)
1 | Local | 30 | 29842472.375 | 58.96% | 16.0714 | 50% | 5431508.25
2 | Import | 9 | 20774609.62 | 41.04% | 48.3333 | 50% | 4674230.2

## Budget_Control
Budget Control — OPEX & CAPEX by Department (BDT)
Department names come from Lists. Enter annual budgets in the BLACK cells. Committed = approved PO value incl. tax. Over Budget > 100%, Watch ≥ threshold in Settings.
Department | OPEX Budget | OPEX Committed | OPEX Utilisation % | CAPEX Budget | CAPEX Committed | CAPEX Utilisation % | Total Budget | Total Committed | Total Paid | Remaining Budget | Utilisation % | Status | Sort key
Cutting | 32000000 | 27935704.85 | 87.3% | 0 | 0 |  | 32000000 | 27935704.85 | 20064877.83 | 4064295.15 | 87.3% | Watch | 32027935.7058
Stitching | 9000000 | 1331038.8 | 14.79% | 6000000 | 0 | 0% | 15000000 | 1331038.8 | 728620.2 | 13668961.2 | 8.874% | Within Budget | 15001331.0398
Lasting & Assembly | 30000000 | 10069342.7 | 33.56% | 4000000 | 0 | 0% | 34000000 | 10069342.7 | 4466881.5 | 23930657.3 | 29.62% | Within Budget | 34010069.3437
Finishing & Packing | 14000000 | 934506.3 | 6.675% | 0 | 0 |  | 14000000 | 934506.3 | 934506.3 | 13065493.7 | 6.675% | Within Budget | 14000934.5073
Product Development | 4000000 | 0 | 0% | 2000000 | 0 | 0% | 6000000 | 0 | 0 | 6000000 | 0% | Within Budget | 6000000.001
Maintenance | 5000000 | 246097.6 | 4.922% | 5000000 | 11792225.795 | 235.8% | 10000000 | 12038323.395 | 6905719.04 | -2038323.395 | 120.4% | Over Budget | 10012038.3244
Store & Warehouse | 3000000 | 0 | 0% | 0 | 0 |  | 3000000 | 0 | 0 | 3000000 | 0% | Within Budget | 3000000.001
Compliance & HSE | 2500000 | 618125 | 24.73% | 0 | 0 |  | 2500000 | 618125 | 365801 | 1881875 | 24.73% | Within Budget | 2500618.126
IT | 1500000 | 0 | 0% | 1500000 | 761820.15 | 50.79% | 3000000 | 761820.15 | 380910.08 | 2238179.85 | 25.39% | Within Budget | 3000761.8211
Admin | 2000000 | 0 | 0% | 0 | 0 |  | 2000000 | 0 | 0 | 2000000 | 0% | Within Budget | 2000000.001
-15
-16
-17
-18
-19
-20
-21
-22
-23
-24
TOTAL | 103000000 | 41134815.25 | 39.94% | 18500000 | 12554045.945 | 67.86% | 121500000 | 53688861.195 | 33847315.95 | 67811138.805 | 44.19% | 1 over / 1 watch
Budget figures are illustrative placeholders — replace with the approved FY 2026-27 budget. Add departments at the bottom of the Lists sheet; budgets stay on the same row as the department.

## Payables_Aging
Accounts Payable Aging — by Supplier (BDT)
Outstanding payable from the register, aged against Next Payment Due Date and the Settings report date. Suppliers come from Lists.
Supplier | Not Yet Due | 1-30 Days | 31-60 Days | 61-90 Days | 90+ Days | No Due Date | Total Outstanding | Overdue Total | % Overdue | Max Days Overdue
Savar Leather Works Ltd | 3668848.05 | 814188.17 | 0 | 0 | 0 | 1383379.2 | 5866415.42 | 814188.17 | 13.88% | 22
Bengal Sole Industries | 859320 | 0 | 0 | 1074150 | 0 | 4129230 | 6062700 | 1074150 | 17.72% | 71
Gazipur Chem Trade | 1175835 | 0 | 0 | 0 | 0 | 272512.5 | 1448347.5 | 0 | 0% | 0
Chattogram Packaging Ltd | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Delta Thread & Trims | 193275.6 | 0 | 108675 | 300468 | 0 | 0 | 602418.6 | 409143 | 67.92% | 70
Narayanganj Board Mills | 0 | 0 | 352800 | 0 | 0 | 0 | 352800 | 352800 | 100% | 31
Dongguan Sole Tech Co. | 2456367.8 | 0 | 0 | 0 | 0 | 0 | 2456367.8 | 0 | 0% | 0
Jiangsu Footwear Machinery Co. | 5092356.36 | 0 | 0 | 0 | 0 | 0 | 5092356.36 | 0 | 0% | 0
Dhaka Spares & Tools | 0 | 185179.5 | 107392.5 | 0 | 0 | 116796.6 | 409368.6 | 292572 | 71.47% | 36
Tech Point BD | 0 | 380910.07 | 0 | 0 | 0 | 0 | 380910.07 | 380910.07 | 100% | 19
TOTAL | 13446002.81 | 1380277.74 | 568867.5 | 1374618 | 0 | 5901918.3 | 22671684.35 | 3323763.24 | 14.66% | 71

## Cash_Forecast
Monthly Procurement Cash View — FY 2026-27 (BDT)
PO commitments by PO month, payments by last payment month, and the outstanding payable falling due each month (cash requirement).
Month Start | Month End | Month | PRs Raised | POs Issued | PO Value incl. Tax | OPEX PO Value | CAPEX PO Value | Cash Paid (by last payment date) | Payable Falling Due | Cumulative PO Value | Cumulative Due
2026-07-01 | 2026-07-31 | Jul-26 | 10 | 10 | 4933028.55 | 4933028.55 | 0 | 3357636.2 | 0 | 4933028.55 | 0
2026-08-01 | 2026-08-31 | Aug-26 | 11 | 10 | 16519153.945 | 3965108 | 12554045.945 | 11603702.52 | 1483293 | 21452182.495 | 1483293
2026-09-01 | 2026-09-30 | Sep-26 | 9 | 9 | 9514011.2 | 9514011.2 | 0 | 9321879.38 | 1695538.74 | 30966193.695 | 3178831.74
2026-10-01 | 2026-10-31 | Oct-26 | 5 | 2 | 6892823.1 | 6892823.1 | 0 | 3986520.85 | 6337449.38 | 37859016.795 | 9516281.12
2026-11-01 | 2026-11-30 | Nov-26 | 0 | 0 | 0 | 0 | 0 | 0 | 7253484.93 | 37859016.795 | 16769766.05
2026-12-01 | 2026-12-31 | Dec-26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37859016.795 | 16769766.05
2027-01-01 | 2027-01-31 | Jan-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37859016.795 | 16769766.05
2027-02-01 | 2027-02-28 | Feb-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37859016.795 | 16769766.05
2027-03-01 | 2027-03-31 | Mar-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37859016.795 | 16769766.05
2027-04-01 | 2027-04-30 | Apr-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37859016.795 | 16769766.05
2027-05-01 | 2027-05-31 | May-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37859016.795 | 16769766.05
2027-06-01 | 2027-06-30 | Jun-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37859016.795 | 16769766.05
|  | TOTAL | 35 | 31 | 37859016.795 | 25304970.85 | 12554045.945 | 28269738.95 | 16769766.05
|  | Overdue before FY | [6 empty] | 0
Note: 'Cash Paid' is booked in the month of the row's Last Payment Date. For exact split by instalment, record each instalment as its own line.
Formulas:
Month End = DATE(YEAR([Month Start]),MONTH([Month Start])+1,0)

## Settings
Settings & Assumptions
BLACK cells (white text) are inputs. Every formula in the workbook reads from here.
Report Date (=TODAY by default; overwrite to freeze a month-end view) | 2026-10-15
Company | Panda Shoes Industry Ltd
OTIF quantity tolerance (received ÷ ordered) | 98%
Price variance alert threshold | 5%
Budget 'Watch' threshold (utilisation) | 85%
Financial year start (Bangladesh FY Jul–Jun) | 2026-07-01
Currency | Rate to BDT | Note
BDT | 1 | Base currency
USD | 122 | Sample rate — replace with bank rate on PO date
CNY | 17 | Sample rate — replace with bank rate on PO date
EUR | 133 | Sample rate — replace with bank rate on PO date
INR | 1.45 | Sample rate — replace with bank rate on PO date
Service levels & analysis thresholds | Value
Approval SLA — max days PR → approval before it is flagged | 3
PO issue SLA — max days approval → PO before it is flagged | 3
ABC class A cut-off (cumulative share of spend) | 80%
ABC class B cut-off (cumulative share of spend) | 95%
Quotations required (count) for a competitive purchase | 3
Quotation threshold — PO value (BDT) from which quotations are required | 100000
Invoice price tolerance vs PO price | 1%

## Lists
Department | Category | Spend Type | Approval Status | Origin | UOM | Currency | Payment Terms | QC / Material Approval | Supplier
Cutting | Leather & Upper | OPEX | Approved | Local | sqft | BDT | 100% Advance | Approved | Savar Leather Works Ltd
Stitching | Synthetic & Textile | CAPEX | Pending | Import | meter | USD | 30% Advance / 70% after In-house | Approved with Deviation | Bengal Sole Industries
Lasting & Assembly | Sole & Bottom |  | Rejected |  | pair | CNY | Credit 30 Days | Rejected | Gazipur Chem Trade
Finishing & Packing | Chemicals & Adhesives |  |  |  | kg | EUR | Credit 60 Days | Pending | Chattogram Packaging Ltd
Product Development | Trims & Accessories |  |  |  | pcs | INR | LC at Sight |  | Delta Thread & Trims
Maintenance | Packaging |  |  |  | sheet |  | 50% Advance / 50% after Installation |  | Narayanganj Board Mills
Store & Warehouse | Spare Parts |  |  |  | cone |  |  |  | Dongguan Sole Tech Co.
Compliance & HSE | Machinery & Equipment |  |  |  | gross |  |  |  | Jiangsu Footwear Machinery Co.
IT | IT Equipment |  |  |  | set |  |  |  | Dhaka Spares & Tools
Admin | Safety & Facility |  |  |  | unit |  |  |  | Tech Point BD
Add new values at the bottom of a column; dropdowns read 40 rows per list. Departments (first 20), Categories (first 20), Payment Terms (first 10) and Suppliers (first 30) feed the analysis sheets automatically.

## Guide
How to use this workbook
Purchase tracking for Panda Shoes Industry Ltd — built for Supply Chain, Finance and Management review.
WORKFLOW
1. PR received | Enter PR No, PR Received Date, Department, Requested By, Item, Category, Spec, Spend Type (OPEX / CAPEX).
2. OPEX / CAPEX approval | Enter Approval Ref, Approval Date, Approval Status, Approved By. Stage moves from 'Awaiting Approval' to 'Approved - PO Pending'.
3. PO order | Enter Supplier, Local/Import, PO No, PO Date, Order Quantity, UOM, Unit Price, Currency, Budget/Standard price and VAT/AIT %. Total Price, FX and price variance calculate automatically.
4. Finance | Enter Payment Terms, then amounts as they are paid: Initial/Advance, Interim, Closing. % of Payment, Outstanding, Finance Status and Aging calculate. Keep Next Payment Due Date and Last Payment Date current.
5. In-house | Enter Supplier Committed Delivery Date, Starting to In-house Date (first receipt), Qty Received (cumulative) and Final In-house Closing Date. Pending Qty, Pending Value and Pending Material Status (All In-house / Pending X / Not Started / Short Closed) calculate, with lead time, delay and OTIF.
6. Material approval | Set QC / Material Approval. Put the approved-sample picture in 'Approved Material Picture' (Excel 365: Insert ▸ Pictures ▸ Place in Cell) and the file path / Drive link in the column beside it.
COLOUR CODE
Black cell, white text (✎ INPUT) | Data-entry cell — the only cells that can be typed in. Dropdown, date and number rules stop wrong entries.
Orange cell | Required input still empty for the stage this line has reached (e.g. PO No entered but PO Date blank).
Grey cell (AUTO) | Formula — locked. Sheets are protected without a password: Review ▸ Unprotect Sheet to change structure, then protect again.
Data Check column | Reads OK when the line is complete and consistent; otherwise lists what to fix (missing fields, dates out of order, overpaid, received > ordered, PO without approval).
Green text | Pulls from another sheet.
Everything else | Automatic — do not type over it. Only black cells take data entry.
SHEETS — WHAT EACH ONE ANSWERS
Dashboard | 25 KPIs, auto-written management highlights and 9 charts. Numbers are in BDT Lakh and shown on every chart.
Action_Tracker | Today's to-do list: every line needing action, sorted High → Medium → Low. Overdue payment, late delivery, approval / PO beyond SLA, price above budget before PO, short closed, QC rejected, advance at risk, data errors.
Purchase_Register | The only place data is entered (black cells). One row per PR line, from PR to final payment.
Supplier_Scorecard | Score 0–100 = 40% OTIF + 20% In-Full + 25% QC acceptance + 15% price discipline. A ≥ 80 Preferred, B 60–79 Approved, C < 60 Review. Also late open POs, short-closed lines, pending value and spend concentration (HHI).
Spend_Analysis | ABC / Pareto of categories (A = first 80% of spend), savings and overspend vs budget price, payment-terms mix (working capital), local vs import.
Budget_Control | OPEX and CAPEX committed vs annual budget by department, with Over Budget / Watch flags.
Payables_Aging | Outstanding payable by supplier: Not Yet Due, 1-30, 31-60, 61-90, 90+ days.
Cash_Forecast | Month-by-month PO commitments, cash paid and payables falling due, for treasury planning.
Settings / Lists | Report date, thresholds, SLAs, ABC cut-offs, FX rates; dropdown lists. New departments, categories and suppliers added at the bottom of Lists flow into every analysis sheet.
KEY METRICS EXPLAINED
OTIF | On Time In Full: closed on or before the supplier's committed date AND at least 98% of the quantity received (tolerance in Settings).
In-Full rate | Share of closed deliveries where the full quantity came in (no short closing).
Price variance vs budget | PO price compared to the budget / standard cost. Negative = saving, positive = overspend.
Price change vs previous PO | Unit price in BDT compared with the most recent earlier PO for the same item name — shows price creep. Keep item names identical.
Paid ahead of receipt | Money paid for goods not yet received — the cash at risk if the supplier fails. On short-closed lines it is the amount to recover.
Cycle-time KPIs | Days PR → Approval, Approval → PO, PO → In-house close and the full cycle — shows where the process waits.
Control breach | Any PO issued without an approved OPEX / CAPEX — an internal-control red flag for audit.
SAMPLE DATA | The 45 sample rows (PR-0045 is a deliberately incomplete demo line), supplier names, budgets and FX rates are illustrative. Before going live, clear the black input cells in Purchase_Register rows 6–50, delete the sample pictures, and enter your real budgets, FX rates and lists.
Prepared by | Abdulla, Manufacturing Resilience, Sustainability & Transformation Division

## Deliveries
ID | PR No | Item / Material Purchased | PO No | Receipt Date | Qty Received | Qty Accepted at QC | Delivery Challan No | Remarks | Entered By | Entered At
GRN-0001 | PSIL-PR-2026-0001 | Cow Nappa Upper Leather | PSIL-PO-2026-0001 | 2026-06-15 | 10500 | 10500 | DC-9656 |  | Sample data
GRN-0002 | PSIL-PR-2026-0002 | Suede Split Leather | PSIL-PO-2026-0002 | 2026-06-25 | 1204 | 1204 | DC-2768 |  | Sample data
GRN-0003 | PSIL-PR-2026-0002 | Suede Split Leather | PSIL-PO-2026-0002 | 2026-06-26 | 3296 | 2802 | DC-7560 |  | Sample data
GRN-0004 | PSIL-PR-2026-0003 | Pig Lining Leather | PSIL-PO-2026-0003 | 2026-07-03 | 8400 | 8400 | DC-1248 |  | Sample data
GRN-0005 | PSIL-PR-2026-0004 | PU Synthetic Leather | PSIL-PO-2026-0004 | 2026-07-26 | 2579 | 2579 | DC-2643 |  | Sample data
GRN-0006 | PSIL-PR-2026-0004 | PU Synthetic Leather | PSIL-PO-2026-0004 | 2026-07-27 | 4821 | 4821 | DC-1689 |  | Sample data
GRN-0007 | PSIL-PR-2026-0005 | Rubber Outsole – Men's Derby | PSIL-PO-2026-0005 | 2026-07-05 | 3023 | 3023 | DC-4220 |  | Sample data
GRN-0008 | PSIL-PR-2026-0005 | Rubber Outsole – Men's Derby | PSIL-PO-2026-0005 | 2026-07-06 | 7416 | 7416 | DC-7360 |  | Sample data
GRN-0009 | PSIL-PR-2026-0006 | TPR Outsole – Ladies Casual | PSIL-PO-2026-0006 | 2026-07-01 | 6800 | 6800 | DC-5591 |  | Sample data
GRN-0010 | PSIL-PR-2026-0007 | EVA Midsole Sheet | PSIL-PO-2026-0007 | 2026-08-13 | 2308 | 2308 | DC-8779 |  | Sample data
GRN-0011 | PSIL-PR-2026-0007 | EVA Midsole Sheet | PSIL-PO-2026-0007 | 2026-08-14 | 2492 | 2492 | DC-6856 |  | Sample data
GRN-0012 | PSIL-PR-2026-0008 | PU Adhesive (Solvent Based) | PSIL-PO-2026-0008 | 2026-07-24 | 448 | 448 | DC-2272 |  | Sample data
GRN-0013 | PSIL-PR-2026-0008 | PU Adhesive (Solvent Based) | PSIL-PO-2026-0008 | 2026-07-26 | 616 | 524 | DC-7834 |  | Sample data
GRN-0014 | PSIL-PR-2026-0009 | Primer & Halogenating Agent | PSIL-PO-2026-0009 | 2026-07-10 | 338 | 338 | DC-8499 |  | Sample data
GRN-0015 | PSIL-PR-2026-0009 | Primer & Halogenating Agent | PSIL-PO-2026-0009 | 2026-07-11 | 362 | 362 | DC-8217 |  | Sample data
GRN-0016 | PSIL-PR-2026-0010 | Bonded Nylon Thread | PSIL-PO-2026-0010 | 2026-07-19 | 448 | 448 | DC-4252 |  | Sample data
GRN-0017 | PSIL-PR-2026-0010 | Bonded Nylon Thread | PSIL-PO-2026-0010 | 2026-07-20 | 563 | 563 | DC-8059 |  | Sample data
GRN-0018 | PSIL-PR-2026-0010 | Bonded Nylon Thread | PSIL-PO-2026-0010 | 2026-07-22 | 340 | 340 | DC-4281 |  | Sample data
GRN-0019 | PSIL-PR-2026-0011 | Metal Eyelets & Hooks | PSIL-PO-2026-0011 | 2026-07-22 | 900 | 900 | DC-1515 |  | Sample data
GRN-0020 | PSIL-PR-2026-0012 | Waxed Cotton Laces | PSIL-PO-2026-0012 | 2026-07-26 | 11700 | 9945 | DC-5364 |  | Sample data
GRN-0021 | PSIL-PR-2026-0013 | Cellulose Insole Board | PSIL-PO-2026-0013 | 2026-08-15 | 2000 | 2000 | DC-9842 |  | Sample data
GRN-0022 | PSIL-PR-2026-0014 | Toe Puff & Counter Sheet | PSIL-PO-2026-0014 | 2026-08-27 | 1422 | 1422 | DC-6249 |  | Sample data
GRN-0023 | PSIL-PR-2026-0014 | Toe Puff & Counter Sheet | PSIL-PO-2026-0014 | 2026-08-28 | 1656 | 1656 | DC-5290 |  | Sample data
GRN-0024 | PSIL-PR-2026-0014 | Toe Puff & Counter Sheet | PSIL-PO-2026-0014 | 2026-08-29 | 622 | 622 | DC-1256 |  | Sample data
GRN-0025 | PSIL-PR-2026-0015 | Shoe Box – Printed | PSIL-PO-2026-0015 | 2026-08-07 | 7603 | 7603 | DC-5754 |  | Sample data
GRN-0026 | PSIL-PR-2026-0015 | Shoe Box – Printed | PSIL-PO-2026-0015 | 2026-08-08 | 6226 | 6226 | DC-3692 |  | Sample data
GRN-0027 | PSIL-PR-2026-0015 | Shoe Box – Printed | PSIL-PO-2026-0015 | 2026-08-10 | 3471 | 3471 | DC-9565 |  | Sample data
GRN-0028 | PSIL-PR-2026-0016 | Export Carton – 5 Ply | PSIL-PO-2026-0016 | 2026-08-04 | 1500 | 1500 | DC-2872 |  | Sample data
GRN-0029 | PSIL-PR-2026-0017 | Sewing Machine Needles & Spares | PSIL-PO-2026-0017 | 2026-08-20 | 13 | 13 | DC-8752 |  | Sample data
GRN-0030 | PSIL-PR-2026-0017 | Sewing Machine Needles & Spares | PSIL-PO-2026-0017 | 2026-08-21 | 27 | 23 | DC-9077 |  | Sample data
GRN-0031 | PSIL-PR-2026-0018 | Safety PPE (Masks, Gloves, Goggles) | PSIL-PO-2026-0018 | 2026-08-09 | 200 | 200 | DC-9363 |  | Sample data
GRN-0032 | PSIL-PR-2026-0019 | Computerised Post-bed Sewing Machine | PSIL-PO-2026-0019 | 2026-09-29 | 7 | 7 | DC-6695 |  | Sample data
GRN-0033 | PSIL-PR-2026-0019 | Computerised Post-bed Sewing Machine | PSIL-PO-2026-0019 | 2026-10-02 | 8 | 8 | DC-3967 |  | Sample data
GRN-0034 | PSIL-PR-2026-0020 | Leather Skiving Machine | PSIL-PO-2026-0020 | 2026-09-29 | 1 | 1 | DC-8898 |  | Sample data
GRN-0035 | PSIL-PR-2026-0020 | Leather Skiving Machine | PSIL-PO-2026-0020 | 2026-09-30 | 2 | 2 | DC-2739 |  | Sample data
GRN-0036 | PSIL-PR-2026-0021 | Hydraulic Sole Pressing Machine | PSIL-PO-2026-0021 | 2026-09-30 | 1 | 1 | DC-1669 |  | Sample data
GRN-0037 | PSIL-PR-2026-0021 | Hydraulic Sole Pressing Machine | PSIL-PO-2026-0021 | 2026-10-01 | 2 | 2 | DC-4281 |  | Sample data
GRN-0038 | PSIL-PR-2026-0022 | Screw Air Compressor 30 HP | PSIL-PO-2026-0022 | 2026-08-27 | 1 | 1 | DC-3622 |  | Sample data
GRN-0039 | PSIL-PR-2026-0023 | Laptop for PPC & Costing Team | PSIL-PO-2026-0023 | 2026-08-27 | 7 | 7 | DC-8681 |  | Sample data
GRN-0040 | PSIL-PR-2026-0024 | Pig Lining Leather | PSIL-PO-2026-0024 | 2026-09-07 | 3959 | 3959 | DC-1826 |  | Sample data
GRN-0041 | PSIL-PR-2026-0024 | Pig Lining Leather | PSIL-PO-2026-0024 | 2026-09-08 | 7341 | 6240 | DC-4202 |  | Sample data
GRN-0042 | PSIL-PR-2026-0025 | Safety PPE (Masks, Gloves, Goggles) | PSIL-PO-2026-0025 | 2026-09-07 | 200 | 200 | DC-7892 |  | Sample data
GRN-0043 | PSIL-PR-2026-0026 | Waxed Cotton Laces | PSIL-PO-2026-0026 | 2026-09-11 | 14100 | 14100 | DC-6230 |  | Sample data
GRN-0044 | PSIL-PR-2026-0027 | Sewing Machine Needles & Spares | PSIL-PO-2026-0027 | 2026-09-09 | 28 | 28 | DC-3290 |  | Sample data
GRN-0045 | PSIL-PR-2026-0027 | Sewing Machine Needles & Spares | PSIL-PO-2026-0027 | 2026-09-12 | 55 | 55 | DC-7831 |  | Sample data
GRN-0046 | PSIL-PR-2026-0030 | Safety PPE (Masks, Gloves, Goggles) | PSIL-PO-2026-0030 | 2026-09-18 | 200 | 200 | DC-8328 |  | Sample data
GRN-0047 | PSIL-PR-2026-0031 | PU Adhesive (Solvent Based) | PSIL-PO-2026-0031 | 2026-09-19 | 411 | 411 | DC-1152 |  | Sample data
GRN-0048 | PSIL-PR-2026-0031 | PU Adhesive (Solvent Based) | PSIL-PO-2026-0031 | 2026-09-20 | 855 | 855 | DC-2246 |  | Sample data
GRN-0049 | PSIL-PR-2026-0032 | TPR Outsole – Ladies Casual | PSIL-PO-2026-0032 | 2026-09-25 | 3165 | 3165 | DC-9456 |  | Sample data
GRN-0050 | PSIL-PR-2026-0032 | TPR Outsole – Ladies Casual | PSIL-PO-2026-0032 | 2026-09-27 | 3268 | 3268 | DC-5068 |  | Sample data
GRN-0051 | PSIL-PR-2026-0033 | Cow Nappa Upper Leather | PSIL-PO-2026-0033 | 2026-09-30 | 6351 | 6351 | DC-7926 |  | Sample data
GRN-0052 | PSIL-PR-2026-0033 | Cow Nappa Upper Leather | PSIL-PO-2026-0033 | 2026-10-03 | 9034 | 9034 | DC-2049 |  | Sample data
GRN-0053 | PSIL-PR-2026-0034 | PU Adhesive (Solvent Based) | PSIL-PO-2026-0034 | 2026-09-19 | 1200 | 1020 | DC-9088 |  | Sample data
GRN-0054 | PSIL-PR-2026-0035 | TPR Outsole – Ladies Casual | PSIL-PO-2026-0035 | 2026-09-24 | 2046 | 2046 | DC-7152 |  | Sample data
GRN-0055 | PSIL-PR-2026-0035 | TPR Outsole – Ladies Casual | PSIL-PO-2026-0035 | 2026-09-25 | 2654 | 2654 | DC-3746 |  | Sample data
GRN-0056 | PSIL-PR-2026-0036 | Waxed Cotton Laces | PSIL-PO-2026-0036 | 2026-10-03 | 5868 | 5868 | DC-8731 |  | Sample data
GRN-0057 | PSIL-PR-2026-0036 | Waxed Cotton Laces | PSIL-PO-2026-0036 | 2026-10-06 | 13132 | 13132 | DC-9333 |  | Sample data
GRN-0058 | PSIL-PR-2026-0038 | Cellulose Insole Board | PSIL-PO-2026-0038 | 2026-10-13 | 1059 | 1059 | DC-3570 |  | Sample data

## Payments
ID | PR No | Item / Material Purchased | PO No | Entry | Payment Type | Date (paid or due) | Amount (BDT) | Invoice No | Settles Planned ID | Bank / Cheque Ref | Remarks | Entered By | Entered At
PAY-0001 | PSIL-PR-2026-0001 | Cow Nappa Upper Leather | PSIL-PO-2026-0001 | Paid | Advance | 2026-06-10 | 948260.25 |  |  | CHQ-166233 |  | Sample data
PAY-0002 | PSIL-PR-2026-0001 | Cow Nappa Upper Leather | PSIL-PO-2026-0001 | Paid | Closing | 2026-06-30 | 2212607.25 |  |  | EFT-162443 |  | Sample data
PAY-0003 | PSIL-PR-2026-0002 | Suede Split Leather | PSIL-PO-2026-0002 | Paid | Advance | 2026-06-13 | 1014552 |  |  | CHQ-213039 |  | Sample data
PAY-0004 | PSIL-PR-2026-0003 | Pig Lining Leather | PSIL-PO-2026-0003 | Paid | Closing | 2026-08-02 | 855540 |  |  | EFT-529969 |  | Sample data
PAY-0005 | PSIL-PR-2026-0004 | PU Synthetic Leather | PSIL-PO-2026-0004 | Paid | Closing | 2026-07-20 | 3228864.2 |  |  | EFT-253468 |  | Sample data
PAY-0006 | PSIL-PR-2026-0005 | Rubber Outsole – Men's Derby | PSIL-PO-2026-0005 | Paid | Interim | 2026-08-05 | 1074150 |  |  | EFT-605954 |  | Sample data
PAY-0007 | PSIL-PR-2026-0005 | Rubber Outsole – Men's Derby | PSIL-PO-2026-0005 | Planned | Closing | 2026-08-05 | 1074150 |  |  |  | Balance per payment terms | Sample data
PAY-0008 | PSIL-PR-2026-0006 | TPR Outsole – Ladies Casual | PSIL-PO-2026-0006 | Paid | Advance | 2026-06-23 | 892500 |  |  | CHQ-322717 |  | Sample data
PAY-0009 | PSIL-PR-2026-0007 | EVA Midsole Sheet | PSIL-PO-2026-0007 | Paid | Closing | 2026-08-04 | 947784 |  |  | EFT-835020 |  | Sample data
PAY-0010 | PSIL-PR-2026-0008 | PU Adhesive (Solvent Based) | PSIL-PO-2026-0008 | Paid | Advance | 2026-06-30 | 509657.5 |  |  | CHQ-928932 |  | Sample data
PAY-0011 | PSIL-PR-2026-0009 | Primer & Halogenating Agent | PSIL-PO-2026-0009 | Paid | Closing | 2026-08-16 | 425915 |  |  | EFT-585094 |  | Sample data
PAY-0012 | PSIL-PR-2026-0010 | Bonded Nylon Thread | PSIL-PO-2026-0010 | Paid | Advance | 2026-07-06 | 128772 |  |  | CHQ-324593 |  | Sample data
PAY-0013 | PSIL-PR-2026-0010 | Bonded Nylon Thread | PSIL-PO-2026-0010 | Planned | Closing | 2026-08-06 | 300468 |  |  |  | Balance per payment terms | Sample data
PAY-0014 | PSIL-PR-2026-0011 | Metal Eyelets & Hooks | PSIL-PO-2026-0011 | Paid | Interim | 2026-08-22 | 108675 |  |  | EFT-391633 |  | Sample data
PAY-0015 | PSIL-PR-2026-0011 | Metal Eyelets & Hooks | PSIL-PO-2026-0011 | Planned | Closing | 2026-08-22 | 108675 |  |  |  | Balance per payment terms | Sample data
PAY-0016 | PSIL-PR-2026-0012 | Waxed Cotton Laces | PSIL-PO-2026-0012 | Paid | Closing | 2026-08-27 | 186117.75 |  |  | EFT-348941 |  | Sample data
PAY-0017 | PSIL-PR-2026-0013 | Cellulose Insole Board | PSIL-PO-2026-0013 | Paid | Interim | 2026-09-14 | 352800 |  |  | EFT-831184 |  | Sample data
PAY-0018 | PSIL-PR-2026-0013 | Cellulose Insole Board | PSIL-PO-2026-0013 | Planned | Closing | 2026-09-14 | 352800 |  |  |  | Balance per payment terms | Sample data
PAY-0019 | PSIL-PR-2026-0014 | Toe Puff & Counter Sheet | PSIL-PO-2026-0014 | Paid | Closing | 2026-08-21 | 1739018.5 |  |  | EFT-465436 |  | Sample data
PAY-0020 | PSIL-PR-2026-0015 | Shoe Box – Printed | PSIL-PO-2026-0015 | Paid | Closing | 2026-09-09 | 712431.3 |  |  | EFT-639193 |  | Sample data
PAY-0021 | PSIL-PR-2026-0016 | Export Carton – 5 Ply | PSIL-PO-2026-0016 | Paid | Advance | 2026-07-25 | 66622.5 |  |  | CHQ-627616 |  | Sample data
PAY-0022 | PSIL-PR-2026-0016 | Export Carton – 5 Ply | PSIL-PO-2026-0016 | Paid | Closing | 2026-08-19 | 155452.5 |  |  | EFT-105175 |  | Sample data
PAY-0023 | PSIL-PR-2026-0017 | Sewing Machine Needles & Spares | PSIL-PO-2026-0017 | Paid | Interim | 2026-09-20 | 40248 |  |  | EFT-233135 |  | Sample data
PAY-0024 | PSIL-PR-2026-0017 | Sewing Machine Needles & Spares | PSIL-PO-2026-0017 | Planned | Closing | 2026-09-20 | 40248 |  |  |  | Balance per payment terms | Sample data
PAY-0025 | PSIL-PR-2026-0018 | Safety PPE (Masks, Gloves, Goggles) | PSIL-PO-2026-0018 | Paid | Interim | 2026-09-09 | 107392.5 |  |  | EFT-753814 |  | Sample data
PAY-0026 | PSIL-PR-2026-0018 | Safety PPE (Masks, Gloves, Goggles) | PSIL-PO-2026-0018 | Planned | Closing | 2026-09-09 | 107392.5 |  |  |  | Balance per payment terms | Sample data
PAY-0027 | PSIL-PR-2026-0019 | Computerised Post-bed Sewing Machine | PSIL-PO-2026-0019 | Paid | Advance | 2026-08-09 | 2779880.68 |  |  | CHQ-431217 |  | Sample data
PAY-0028 | PSIL-PR-2026-0019 | Computerised Post-bed Sewing Machine | PSIL-PO-2026-0019 | Planned | Closing | 2026-11-01 | 2779880.68 |  |  |  | Balance per payment terms | Sample data
PAY-0029 | PSIL-PR-2026-0020 | Leather Skiving Machine | PSIL-PO-2026-0020 | Paid | Advance | 2026-08-11 | 786511.45 |  |  | CHQ-125485 |  | Sample data
PAY-0030 | PSIL-PR-2026-0020 | Leather Skiving Machine | PSIL-PO-2026-0020 | Planned | Closing | 2026-10-30 | 786511.46 |  |  |  | Balance per payment terms | Sample data
PAY-0031 | PSIL-PR-2026-0021 | Hydraulic Sole Pressing Machine | PSIL-PO-2026-0021 | Paid | Advance | 2026-08-17 | 1525964.23 |  |  | CHQ-290074 |  | Sample data
PAY-0032 | PSIL-PR-2026-0021 | Hydraulic Sole Pressing Machine | PSIL-PO-2026-0021 | Planned | Closing | 2026-10-31 | 1525964.22 |  |  |  | Balance per payment terms | Sample data
PAY-0033 | PSIL-PR-2026-0022 | Screw Air Compressor 30 HP | PSIL-PO-2026-0022 | Paid | Advance | 2026-08-14 | 803756.54 |  |  | CHQ-954213 |  | Sample data
PAY-0034 | PSIL-PR-2026-0022 | Screw Air Compressor 30 HP | PSIL-PO-2026-0022 | Paid | Closing | 2026-09-26 | 803756.54 |  |  | EFT-525340 |  | Sample data
PAY-0035 | PSIL-PR-2026-0023 | Laptop for PPC & Costing Team | PSIL-PO-2026-0023 | Paid | Advance | 2026-08-19 | 380910.08 |  |  | CHQ-205762 |  | Sample data
PAY-0036 | PSIL-PR-2026-0023 | Laptop for PPC & Costing Team | PSIL-PO-2026-0023 | Planned | Closing | 2026-09-26 | 380910.07 |  |  |  | Balance per payment terms | Sample data
PAY-0037 | PSIL-PR-2026-0024 | Pig Lining Leather | PSIL-PO-2026-0024 | Paid | Advance | 2026-08-19 | 348937.78 |  |  | CHQ-779487 |  | Sample data
PAY-0038 | PSIL-PR-2026-0024 | Pig Lining Leather | PSIL-PO-2026-0024 | Planned | Closing | 2026-09-23 | 814188.17 |  |  |  | Balance per payment terms | Sample data
PAY-0039 | PSIL-PR-2026-0025 | Safety PPE (Masks, Gloves, Goggles) | PSIL-PO-2026-0025 | Paid | Closing | 2026-10-07 | 196295 |  |  | EFT-398252 |  | Sample data
PAY-0040 | PSIL-PR-2026-0026 | Waxed Cotton Laces | PSIL-PO-2026-0026 | Paid | Advance | 2026-08-23 | 222223.05 |  |  | CHQ-177074 |  | Sample data
PAY-0041 | PSIL-PR-2026-0027 | Sewing Machine Needles & Spares | PSIL-PO-2026-0027 | Paid | Advance | 2026-08-24 | 49680.48 |  |  | CHQ-577682 |  | Sample data
PAY-0042 | PSIL-PR-2026-0027 | Sewing Machine Needles & Spares | PSIL-PO-2026-0027 | Paid | Closing | 2026-09-27 | 115921.12 |  |  | EFT-730247 |  | Sample data
PAY-0043 | PSIL-PR-2026-0029 | PU Synthetic Leather | PSIL-PO-2026-0029 | Paid | Closing | 2026-10-06 | 2217862.4 |  |  | EFT-753628 |  | Sample data
PAY-0044 | PSIL-PR-2026-0030 | Safety PPE (Masks, Gloves, Goggles) | PSIL-PO-2026-0030 | Paid | Advance | 2026-09-06 | 62113.5 |  |  | CHQ-948489 |  | Sample data
PAY-0045 | PSIL-PR-2026-0030 | Safety PPE (Masks, Gloves, Goggles) | PSIL-PO-2026-0030 | Planned | Closing | 2026-10-03 | 144931.5 |  |  |  | Balance per payment terms | Sample data
PAY-0046 | PSIL-PR-2026-0031 | PU Adhesive (Solvent Based) | PSIL-PO-2026-0031 | Planned | Closing | 2026-10-20 | 612105 |  |  |  | Balance per payment terms | Sample data
PAY-0047 | PSIL-PR-2026-0032 | TPR Outsole – Ladies Casual | PSIL-PO-2026-0032 | Planned | Closing | 2026-10-27 | 859320 |  |  |  | Balance per payment terms | Sample data
PAY-0048 | PSIL-PR-2026-0033 | Cow Nappa Upper Leather | PSIL-PO-2026-0033 | Paid | Advance | 2026-09-17 | 5011272 |  |  | CHQ-710229 |  | Sample data
PAY-0049 | PSIL-PR-2026-0034 | PU Adhesive (Solvent Based) | PSIL-PO-2026-0034 | Planned | Closing | 2026-10-19 | 563730 |  |  |  | Balance per payment terms | Sample data
PAY-0050 | PSIL-PR-2026-0035 | TPR Outsole – Ladies Casual | PSIL-PO-2026-0035 | Paid | Advance | 2026-09-19 | 616875 |  |  | CHQ-436466 |  | Sample data
PAY-0051 | PSIL-PR-2026-0036 | Waxed Cotton Laces | PSIL-PO-2026-0036 | Paid | Advance | 2026-09-24 | 82832.4 |  |  | CHQ-334838 |  | Sample data
PAY-0052 | PSIL-PR-2026-0036 | Waxed Cotton Laces | PSIL-PO-2026-0036 | Planned | Closing | 2026-10-21 | 193275.6 |  |  |  | Balance per payment terms | Sample data
PAY-0053 | PSIL-PR-2026-0037 | EVA Midsole Sheet | PSIL-PO-2026-0037 | Planned | Closing | 2026-11-05 | 804756.2 |  |  |  | Balance per payment terms | Sample data
PAY-0054 | PSIL-PR-2026-0038 | Cellulose Insole Board | PSIL-PO-2026-0038 | Paid | Advance | 2026-09-27 | 562800 |  |  | CHQ-909429 |  | Sample data
PAY-0055 | PSIL-PR-2026-0040 | Toe Puff & Counter Sheet | PSIL-PO-2026-0040 | Planned | Closing | 2026-10-26 | 1651611.6 |  |  |  | Balance per payment terms | Sample data
PAY-0056 | PSIL-PR-2026-0042 | Cow Nappa Upper Leather | PSIL-PO-2026-0042 | Paid | Advance | 2026-10-09 | 1572363.45 |  |  | CHQ-494252 |  | Sample data
PAY-0057 | PSIL-PR-2026-0042 | Cow Nappa Upper Leather | PSIL-PO-2026-0042 | Planned | Closing | 2026-11-12 | 3668848.05 |  |  |  | Balance per payment terms | Sample data

## Quotations
ID | PR No | Item / Material Purchased | PO No | Supplier | Quote Date | Unit Price | Currency | Quoted Lead Time (days) | Payment Terms | Remarks | Entered By | Entered At
QT-0001 | PSIL-PR-2026-0001 | Cow Nappa Upper Leather | PSIL-PO-2026-0001 | Savar Leather Works Ltd | 2026-06-02 | 2.35 | USD | 35 | Credit 30 Days |  | Sample data
QT-0002 | PSIL-PR-2026-0001 | Cow Nappa Upper Leather | PSIL-PO-2026-0001 | Chattogram Packaging Ltd | 2026-06-02 | 2.47 | USD | 45 | Credit 60 Days |  | Sample data
QT-0003 | PSIL-PR-2026-0001 | Cow Nappa Upper Leather | PSIL-PO-2026-0001 | Jiangsu Footwear Machinery Co. | 2026-06-02 | 2.76 | USD | 46 | 100% Advance |  | Sample data
QT-0004 | PSIL-PR-2026-0002 | Suede Split Leather | PSIL-PO-2026-0002 | Savar Leather Works Ltd | 2026-06-06 | 1.76 | USD | 48 | Credit 30 Days |  | Sample data
QT-0005 | PSIL-PR-2026-0002 | Suede Split Leather | PSIL-PO-2026-0002 | Bengal Sole Industries | 2026-06-07 | 1.92 | USD | 60 | 100% Advance |  | Sample data
QT-0006 | PSIL-PR-2026-0002 | Suede Split Leather | PSIL-PO-2026-0002 | Jiangsu Footwear Machinery Co. | 2026-06-06 | 2 | USD | 55 | 30% Advance / 70% after In-house |  | Sample data
QT-0007 | PSIL-PR-2026-0003 | Pig Lining Leather | PSIL-PO-2026-0003 | Savar Leather Works Ltd | 2026-06-09 | 97 | BDT | 33 | 100% Advance |  | Sample data
QT-0008 | PSIL-PR-2026-0003 | Pig Lining Leather | PSIL-PO-2026-0003 | Delta Thread & Trims | 2026-06-08 | 108.15 | BDT | 56 | 50% Advance / 50% after Installation |  | Sample data
QT-0009 | PSIL-PR-2026-0003 | Pig Lining Leather | PSIL-PO-2026-0003 | Chattogram Packaging Ltd | 2026-06-08 | 103.84 | BDT | 26 | Credit 30 Days |  | Sample data
QT-0010 | PSIL-PR-2026-0004 | PU Synthetic Leather | PSIL-PO-2026-0004 | Delta Thread & Trims | 2026-06-12 | 3.54 | USD | 33 | 50% Advance / 50% after Installation |  | Sample data
QT-0011 | PSIL-PR-2026-0004 | PU Synthetic Leather | PSIL-PO-2026-0004 | Jiangsu Footwear Machinery Co. | 2026-06-14 | 3.38 | USD | 33 | 30% Advance / 70% after In-house |  | Sample data
QT-0012 | PSIL-PR-2026-0004 | PU Synthetic Leather | PSIL-PO-2026-0004 | Gazipur Chem Trade | 2026-06-15 | 3.2 | USD | 26 | 100% Advance |  | Sample data
QT-0013 | PSIL-PR-2026-0005 | Rubber Outsole – Men's Derby | PSIL-PO-2026-0005 | Bengal Sole Industries | 2026-06-15 | 186 | BDT | 30 | LC at Sight |  | Sample data
QT-0014 | PSIL-PR-2026-0005 | Rubber Outsole – Men's Derby | PSIL-PO-2026-0005 | Gazipur Chem Trade | 2026-06-15 | 177 | BDT | 60 | LC at Sight |  | Sample data
QT-0015 | PSIL-PR-2026-0005 | Rubber Outsole – Men's Derby | PSIL-PO-2026-0005 | Chattogram Packaging Ltd | 2026-06-15 | 195 | BDT | 18 | 50% Advance / 50% after Installation |  | Sample data
QT-0016 | PSIL-PR-2026-0005 | Rubber Outsole – Men's Derby | PSIL-PO-2026-0005 | Jiangsu Footwear Machinery Co. | 2026-06-14 | 196 | BDT | 59 | LC at Sight |  | Sample data
QT-0017 | PSIL-PR-2026-0006 | TPR Outsole – Ladies Casual | PSIL-PO-2026-0006 | Bengal Sole Industries | 2026-06-21 | 125 | BDT | 38 | Credit 30 Days |  | Sample data
QT-0018 | PSIL-PR-2026-0006 | TPR Outsole – Ladies Casual | PSIL-PO-2026-0006 | Dhaka Spares & Tools | 2026-06-17 | 139 | BDT | 15 | 30% Advance / 70% after In-house |  | Sample data
QT-0019 | PSIL-PR-2026-0006 | TPR Outsole – Ladies Casual | PSIL-PO-2026-0006 | Dongguan Sole Tech Co. | 2026-06-21 | 138 | BDT | 46 | 100% Advance |  | Sample data
QT-0020 | PSIL-PR-2026-0007 | EVA Midsole Sheet | PSIL-PO-2026-0007 | Dongguan Sole Tech Co. | 2026-06-23 | 10.1 | CNY | 40 | LC at Sight |  | Sample data
QT-0021 | PSIL-PR-2026-0007 | EVA Midsole Sheet | PSIL-PO-2026-0007 | Delta Thread & Trims | 2026-06-21 | 9.88 | CNY | 30 | 30% Advance / 70% after In-house |  | Sample data
QT-0022 | PSIL-PR-2026-0007 | EVA Midsole Sheet | PSIL-PO-2026-0007 | Jiangsu Footwear Machinery Co. | 2026-06-23 | 11.75 | CNY | 49 | 50% Advance / 50% after Installation |  | Sample data
QT-0023 | PSIL-PR-2026-0008 | PU Adhesive (Solvent Based) | PSIL-PO-2026-0008 | Gazipur Chem Trade | 2026-06-27 | 431 | BDT | 30 | 50% Advance / 50% after Installation |  | Sample data
QT-0024 | PSIL-PR-2026-0008 | PU Adhesive (Solvent Based) | PSIL-PO-2026-0008 | Tech Point BD | 2026-06-24 | 402 | BDT | 57 | Credit 30 Days |  | Sample data
QT-0025 | PSIL-PR-2026-0009 | Primer & Halogenating Agent | PSIL-PO-2026-0009 | Gazipur Chem Trade | 2026-06-27 | 566 | BDT | 23 | Credit 60 Days |  | Sample data
QT-0026 | PSIL-PR-2026-0010 | Bonded Nylon Thread | PSIL-PO-2026-0010 | Delta Thread & Trims | 2026-06-29 | 292 | BDT | 38 | LC at Sight |  | Sample data
QT-0027 | PSIL-PR-2026-0010 | Bonded Nylon Thread | PSIL-PO-2026-0010 | Bengal Sole Industries | 2026-07-02 | 330 | BDT | 23 | 100% Advance |  | Sample data
QT-0028 | PSIL-PR-2026-0010 | Bonded Nylon Thread | PSIL-PO-2026-0010 | Jiangsu Footwear Machinery Co. | 2026-06-30 | 317 | BDT | 50 | LC at Sight |  | Sample data
QT-0029 | PSIL-PR-2026-0010 | Bonded Nylon Thread | PSIL-PO-2026-0010 | Dongguan Sole Tech Co. | 2026-06-30 | 310 | BDT | 55 | Credit 30 Days |  | Sample data
QT-0030 | PSIL-PR-2026-0011 | Metal Eyelets & Hooks | PSIL-PO-2026-0011 | Delta Thread & Trims | 2026-07-04 | 230 | BDT | 20 | Credit 60 Days |  | Sample data
QT-0031 | PSIL-PR-2026-0011 | Metal Eyelets & Hooks | PSIL-PO-2026-0011 | Bengal Sole Industries | 2026-07-06 | 250 | BDT | 38 | 50% Advance / 50% after Installation |  | Sample data
QT-0032 | PSIL-PR-2026-0011 | Metal Eyelets & Hooks | PSIL-PO-2026-0011 | Chattogram Packaging Ltd | 2026-07-06 | 248 | BDT | 35 | Credit 30 Days |  | Sample data
QT-0033 | PSIL-PR-2026-0012 | Waxed Cotton Laces | PSIL-PO-2026-0012 | Delta Thread & Trims | 2026-07-07 | 15.15 | BDT | 36 | 30% Advance / 70% after In-house |  | Sample data
QT-0034 | PSIL-PR-2026-0013 | Cellulose Insole Board | PSIL-PO-2026-0013 | Narayanganj Board Mills | 2026-07-11 | 336 | BDT | 23 | 30% Advance / 70% after In-house |  | Sample data
QT-0035 | PSIL-PR-2026-0013 | Cellulose Insole Board | PSIL-PO-2026-0013 | Tech Point BD | 2026-07-11 | 382 | BDT | 41 | 50% Advance / 50% after Installation |  | Sample data
QT-0036 | PSIL-PR-2026-0013 | Cellulose Insole Board | PSIL-PO-2026-0013 | Chattogram Packaging Ltd | 2026-07-09 | 348 | BDT | 24 | Credit 30 Days |  | Sample data
QT-0037 | PSIL-PR-2026-0014 | Toe Puff & Counter Sheet | PSIL-PO-2026-0014 | Dongguan Sole Tech Co. | 2026-07-10 | 3.35 | USD | 31 | LC at Sight |  | Sample data
QT-0038 | PSIL-PR-2026-0014 | Toe Puff & Counter Sheet | PSIL-PO-2026-0014 | Savar Leather Works Ltd | 2026-07-11 | 3.74 | USD | 36 | Credit 30 Days |  | Sample data
QT-0039 | PSIL-PR-2026-0014 | Toe Puff & Counter Sheet | PSIL-PO-2026-0014 | Gazipur Chem Trade | 2026-07-10 | 3.78 | USD | 13 | 50% Advance / 50% after Installation |  | Sample data
QT-0040 | PSIL-PR-2026-0014 | Toe Puff & Counter Sheet | PSIL-PO-2026-0014 | Delta Thread & Trims | 2026-07-10 | 3.89 | USD | 20 | 30% Advance / 70% after In-house |  | Sample data
QT-0041 | PSIL-PR-2026-0015 | Shoe Box – Printed | PSIL-PO-2026-0015 | Chattogram Packaging Ltd | 2026-07-14 | 39.22 | BDT | 18 | LC at Sight |  | Sample data
QT-0042 | PSIL-PR-2026-0015 | Shoe Box – Printed | PSIL-PO-2026-0015 | Bengal Sole Industries | 2026-07-14 | 42.37 | BDT | 37 | 30% Advance / 70% after In-house |  | Sample data
QT-0043 | PSIL-PR-2026-0015 | Shoe Box – Printed | PSIL-PO-2026-0015 | Dongguan Sole Tech Co. | 2026-07-16 | 46.28 | BDT | 40 | 50% Advance / 50% after Installation |  | Sample data
QT-0044 | PSIL-PR-2026-0016 | Export Carton – 5 Ply | PSIL-PO-2026-0016 | Chattogram Packaging Ltd | 2026-07-18 | 141 | BDT | 33 | LC at Sight |  | Sample data
QT-0045 | PSIL-PR-2026-0017 | Sewing Machine Needles & Spares | PSIL-PO-2026-0017 | Dhaka Spares & Tools | 2026-07-21 | 1872 | BDT | 41 | Credit 60 Days |  | Sample data
QT-0046 | PSIL-PR-2026-0018 | Safety PPE (Masks, Gloves, Goggles) | PSIL-PO-2026-0018 | Dhaka Spares & Tools | 2026-07-23 | 999 | BDT | 21 | 100% Advance |  | Sample data
QT-0047 | PSIL-PR-2026-0018 | Safety PPE (Masks, Gloves, Goggles) | PSIL-PO-2026-0018 | Tech Point BD | 2026-07-24 | 963 | BDT | 53 | Credit 30 Days |  | Sample data
QT-0048 | PSIL-PR-2026-0018 | Safety PPE (Masks, Gloves, Goggles) | PSIL-PO-2026-0018 | Dongguan Sole Tech Co. | 2026-07-24 | 1066 | BDT | 13 | Credit 60 Days |  | Sample data
QT-0049 | PSIL-PR-2026-0019 | Computerised Post-bed Sewing Machine | PSIL-PO-2026-0019 | Jiangsu Footwear Machinery Co. | 2026-07-31 | 2543.07 | USD | 47 | 30% Advance / 70% after In-house |  | Sample data
QT-0050 | PSIL-PR-2026-0019 | Computerised Post-bed Sewing Machine | PSIL-PO-2026-0019 | Delta Thread & Trims | 2026-07-31 | 2821 | USD | 46 | LC at Sight |  | Sample data
QT-0051 | PSIL-PR-2026-0020 | Leather Skiving Machine | PSIL-PO-2026-0020 | Jiangsu Footwear Machinery Co. | 2026-08-04 | 3837.39 | USD | 41 | 50% Advance / 50% after Installation |  | Sample data
QT-0052 | PSIL-PR-2026-0020 | Leather Skiving Machine | PSIL-PO-2026-0020 | Tech Point BD | 2026-08-04 | 3593 | USD | 47 | 50% Advance / 50% after Installation |  | Sample data
QT-0053 | PSIL-PR-2026-0020 | Leather Skiving Machine | PSIL-PO-2026-0020 | Gazipur Chem Trade | 2026-07-30 | 4412 | USD | 19 | LC at Sight |  | Sample data
QT-0054 | PSIL-PR-2026-0020 | Leather Skiving Machine | PSIL-PO-2026-0020 | Delta Thread & Trims | 2026-08-03 | 4345 | USD | 14 | 50% Advance / 50% after Installation |  | Sample data
QT-0055 | PSIL-PR-2026-0021 | Hydraulic Sole Pressing Machine | PSIL-PO-2026-0021 | Jiangsu Footwear Machinery Co. | 2026-08-03 | 53430.12 | CNY | 50 | Credit 60 Days |  | Sample data
QT-0056 | PSIL-PR-2026-0021 | Hydraulic Sole Pressing Machine | PSIL-PO-2026-0021 | Delta Thread & Trims | 2026-08-02 | 55655 | CNY | 27 | Credit 60 Days |  | Sample data
QT-0057 | PSIL-PR-2026-0021 | Hydraulic Sole Pressing Machine | PSIL-PO-2026-0021 | Savar Leather Works Ltd | 2026-08-09 | 58775 | CNY | 29 | Credit 60 Days |  | Sample data
QT-0058 | PSIL-PR-2026-0022 | Screw Air Compressor 30 HP | PSIL-PO-2026-0022 | Dhaka Spares & Tools | 2026-08-05 | 1495361 | BDT | 39 | LC at Sight |  | Sample data
QT-0059 | PSIL-PR-2026-0022 | Screw Air Compressor 30 HP | PSIL-PO-2026-0022 | Chattogram Packaging Ltd | 2026-08-10 | 1760641 | BDT | 55 | Credit 30 Days |  | Sample data
QT-0060 | PSIL-PR-2026-0022 | Screw Air Compressor 30 HP | PSIL-PO-2026-0022 | Jiangsu Footwear Machinery Co. | 2026-08-04 | 1602918 | BDT | 54 | 50% Advance / 50% after Installation |  | Sample data
QT-0061 | PSIL-PR-2026-0023 | Laptop for PPC & Costing Team | PSIL-PO-2026-0023 | Tech Point BD | 2026-08-09 | 103649 | BDT | 28 | Credit 30 Days |  | Sample data
QT-0062 | PSIL-PR-2026-0024 | Pig Lining Leather | PSIL-PO-2026-0024 | Savar Leather Works Ltd | 2026-08-12 | 98.03 | BDT | 48 | 30% Advance / 70% after In-house |  | Sample data
QT-0063 | PSIL-PR-2026-0024 | Pig Lining Leather | PSIL-PO-2026-0024 | Tech Point BD | 2026-08-12 | 111.28 | BDT | 43 | 100% Advance |  | Sample data
QT-0064 | PSIL-PR-2026-0024 | Pig Lining Leather | PSIL-PO-2026-0024 | Bengal Sole Industries | 2026-08-11 | 102.66 | BDT | 54 | 30% Advance / 70% after In-house |  | Sample data
QT-0065 | PSIL-PR-2026-0025 | Safety PPE (Masks, Gloves, Goggles) | PSIL-PO-2026-0025 | Dhaka Spares & Tools | 2026-08-13 | 913 | BDT | 31 | 30% Advance / 70% after In-house |  | Sample data
QT-0066 | PSIL-PR-2026-0025 | Safety PPE (Masks, Gloves, Goggles) | PSIL-PO-2026-0025 | Bengal Sole Industries | 2026-08-14 | 993 | BDT | 38 | LC at Sight |  | Sample data
QT-0067 | PSIL-PR-2026-0025 | Safety PPE (Masks, Gloves, Goggles) | PSIL-PO-2026-0025 | Narayanganj Board Mills | 2026-08-13 | 1024 | BDT | 34 | Credit 60 Days |  | Sample data
QT-0068 | PSIL-PR-2026-0026 | Waxed Cotton Laces | PSIL-PO-2026-0026 | Delta Thread & Trims | 2026-08-16 | 15.01 | BDT | 44 | 100% Advance |  | Sample data
QT-0069 | PSIL-PR-2026-0026 | Waxed Cotton Laces | PSIL-PO-2026-0026 | Savar Leather Works Ltd | 2026-08-17 | 14.43 | BDT | 55 | 50% Advance / 50% after Installation |  | Sample data
QT-0070 | PSIL-PR-2026-0026 | Waxed Cotton Laces | PSIL-PO-2026-0026 | Bengal Sole Industries | 2026-08-17 | 16.34 | BDT | 54 | Credit 60 Days |  | Sample data
QT-0071 | PSIL-PR-2026-0027 | Sewing Machine Needles & Spares | PSIL-PO-2026-0027 | Dhaka Spares & Tools | 2026-08-20 | 1856 | BDT | 45 | 50% Advance / 50% after Installation |  | Sample data
QT-0072 | PSIL-PR-2026-0027 | Sewing Machine Needles & Spares | PSIL-PO-2026-0027 | Chattogram Packaging Ltd | 2026-08-21 | 1737 | BDT | 36 | 100% Advance |  | Sample data
QT-0073 | PSIL-PR-2026-0027 | Sewing Machine Needles & Spares | PSIL-PO-2026-0027 | Narayanganj Board Mills | 2026-08-20 | 1968 | BDT | 29 | LC at Sight |  | Sample data
QT-0074 | PSIL-PR-2026-0028 | Sewing Machine Needles & Spares |  | Dhaka Spares & Tools | 2026-08-22 | 2012 | BDT | 39 | Credit 30 Days |  | Sample data
QT-0075 | PSIL-PR-2026-0028 | Sewing Machine Needles & Spares |  | Gazipur Chem Trade | 2026-08-24 | 2309 | BDT | 24 | Credit 30 Days |  | Sample data
QT-0076 | PSIL-PR-2026-0029 | PU Synthetic Leather | PSIL-PO-2026-0029 | Dongguan Sole Tech Co. | 2026-08-25 | 3.04 | USD | 47 | 100% Advance |  | Sample data
QT-0077 | PSIL-PR-2026-0029 | PU Synthetic Leather | PSIL-PO-2026-0029 | Tech Point BD | 2026-08-26 | 3.14 | USD | 34 | 100% Advance |  | Sample data
QT-0078 | PSIL-PR-2026-0030 | Safety PPE (Masks, Gloves, Goggles) | PSIL-PO-2026-0030 | Dhaka Spares & Tools | 2026-09-01 | 963 | BDT | 37 | Credit 60 Days |  | Sample data
QT-0079 | PSIL-PR-2026-0030 | Safety PPE (Masks, Gloves, Goggles) | PSIL-PO-2026-0030 | Tech Point BD | 2026-09-01 | 1043 | BDT | 28 | Credit 60 Days |  | Sample data
QT-0080 | PSIL-PR-2026-0030 | Safety PPE (Masks, Gloves, Goggles) | PSIL-PO-2026-0030 | Jiangsu Footwear Machinery Co. | 2026-08-30 | 1099 | BDT | 58 | 100% Advance |  | Sample data
QT-0081 | PSIL-PR-2026-0031 | PU Adhesive (Solvent Based) | PSIL-PO-2026-0031 | Gazipur Chem Trade | 2026-09-02 | 438 | BDT | 25 | LC at Sight |  | Sample data
QT-0082 | PSIL-PR-2026-0031 | PU Adhesive (Solvent Based) | PSIL-PO-2026-0031 | Narayanganj Board Mills | 2026-09-01 | 424 | BDT | 34 | 50% Advance / 50% after Installation |  | Sample data
QT-0083 | PSIL-PR-2026-0031 | PU Adhesive (Solvent Based) | PSIL-PO-2026-0031 | Bengal Sole Industries | 2026-08-31 | 475 | BDT | 36 | Credit 30 Days |  | Sample data
QT-0084 | PSIL-PR-2026-0031 | PU Adhesive (Solvent Based) | PSIL-PO-2026-0031 | Savar Leather Works Ltd | 2026-08-31 | 456 | BDT | 34 | LC at Sight |  | Sample data
QT-0085 | PSIL-PR-2026-0032 | TPR Outsole – Ladies Casual | PSIL-PO-2026-0032 | Bengal Sole Industries | 2026-09-03 | 124 | BDT | 27 | 50% Advance / 50% after Installation |  | Sample data
QT-0086 | PSIL-PR-2026-0032 | TPR Outsole – Ladies Casual | PSIL-PO-2026-0032 | Savar Leather Works Ltd | 2026-09-05 | 136 | BDT | 50 | Credit 30 Days |  | Sample data
QT-0087 | PSIL-PR-2026-0032 | TPR Outsole – Ladies Casual | PSIL-PO-2026-0032 | Narayanganj Board Mills | 2026-09-04 | 136 | BDT | 36 | Credit 30 Days |  | Sample data
QT-0088 | PSIL-PR-2026-0033 | Cow Nappa Upper Leather | PSIL-PO-2026-0033 | Savar Leather Works Ltd | 2026-09-12 | 2.4 | USD | 18 | 30% Advance / 70% after In-house |  | Sample data
QT-0089 | PSIL-PR-2026-0033 | Cow Nappa Upper Leather | PSIL-PO-2026-0033 | Delta Thread & Trims | 2026-09-11 | 2.5 | USD | 25 | 100% Advance |  | Sample data
QT-0090 | PSIL-PR-2026-0033 | Cow Nappa Upper Leather | PSIL-PO-2026-0033 | Bengal Sole Industries | 2026-09-08 | 2.55 | USD | 41 | 30% Advance / 70% after In-house |  | Sample data
QT-0091 | PSIL-PR-2026-0034 | PU Adhesive (Solvent Based) | PSIL-PO-2026-0034 | Gazipur Chem Trade | 2026-09-10 | 437 | BDT | 38 | LC at Sight |  | Sample data
QT-0092 | PSIL-PR-2026-0034 | PU Adhesive (Solvent Based) | PSIL-PO-2026-0034 | Jiangsu Footwear Machinery Co. | 2026-09-11 | 472 | BDT | 32 | Credit 30 Days |  | Sample data
QT-0093 | PSIL-PR-2026-0034 | PU Adhesive (Solvent Based) | PSIL-PO-2026-0034 | Delta Thread & Trims | 2026-09-11 | 472 | BDT | 50 | 30% Advance / 70% after In-house |  | Sample data
QT-0094 | PSIL-PR-2026-0035 | TPR Outsole – Ladies Casual | PSIL-PO-2026-0035 | Bengal Sole Industries | 2026-09-12 | 125 | BDT | 40 | Credit 30 Days |  | Sample data
QT-0095 | PSIL-PR-2026-0035 | TPR Outsole – Ladies Casual | PSIL-PO-2026-0035 | Narayanganj Board Mills | 2026-09-12 | 142 | BDT | 33 | Credit 60 Days |  | Sample data
QT-0096 | PSIL-PR-2026-0036 | Waxed Cotton Laces | PSIL-PO-2026-0036 | Delta Thread & Trims | 2026-09-17 | 13.84 | BDT | 10 | Credit 60 Days |  | Sample data
QT-0097 | PSIL-PR-2026-0036 | Waxed Cotton Laces | PSIL-PO-2026-0036 | Bengal Sole Industries | 2026-09-19 | 14.29 | BDT | 58 | 100% Advance |  | Sample data
QT-0098 | PSIL-PR-2026-0036 | Waxed Cotton Laces | PSIL-PO-2026-0036 | Tech Point BD | 2026-09-17 | 14.9 | BDT | 18 | Credit 30 Days |  | Sample data
QT-0099 | PSIL-PR-2026-0037 | EVA Midsole Sheet | PSIL-PO-2026-0037 | Dongguan Sole Tech Co. | 2026-09-18 | 10.04 | CNY | 32 | 100% Advance |  | Sample data
QT-0100 | PSIL-PR-2026-0037 | EVA Midsole Sheet | PSIL-PO-2026-0037 | Narayanganj Board Mills | 2026-09-18 | 10.67 | CNY | 58 | Credit 60 Days |  | Sample data
QT-0101 | PSIL-PR-2026-0037 | EVA Midsole Sheet | PSIL-PO-2026-0037 | Savar Leather Works Ltd | 2026-09-19 | 11.81 | CNY | 57 | 100% Advance |  | Sample data
QT-0102 | PSIL-PR-2026-0038 | Cellulose Insole Board | PSIL-PO-2026-0038 | Narayanganj Board Mills | 2026-09-23 | 335 | BDT | 17 | Credit 60 Days |  | Sample data
QT-0103 | PSIL-PR-2026-0039 | Rubber Outsole – Men's Derby |  | Bengal Sole Industries | 2026-09-24 | 197 | BDT | 29 | Credit 30 Days |  | Sample data
QT-0104 | PSIL-PR-2026-0039 | Rubber Outsole – Men's Derby |  | Dongguan Sole Tech Co. | 2026-09-24 | 221 | BDT | 37 | 50% Advance / 50% after Installation |  | Sample data
QT-0105 | PSIL-PR-2026-0039 | Rubber Outsole – Men's Derby |  | Chattogram Packaging Ltd | 2026-09-24 | 217 | BDT | 8 | 30% Advance / 70% after In-house |  | Sample data
QT-0106 | PSIL-PR-2026-0040 | Toe Puff & Counter Sheet | PSIL-PO-2026-0040 | Dongguan Sole Tech Co. | 2026-09-29 | 3.27 | USD | 26 | Credit 30 Days |  | Sample data
QT-0107 | PSIL-PR-2026-0040 | Toe Puff & Counter Sheet | PSIL-PO-2026-0040 | Narayanganj Board Mills | 2026-09-29 | 3.52 | USD | 42 | Credit 30 Days |  | Sample data
QT-0108 | PSIL-PR-2026-0040 | Toe Puff & Counter Sheet | PSIL-PO-2026-0040 | Delta Thread & Trims | 2026-09-29 | 3.86 | USD | 30 | 100% Advance |  | Sample data
QT-0109 | PSIL-PR-2026-0041 | Rubber Outsole – Men's Derby |  | Bengal Sole Industries | 2026-10-02 | 201 | BDT | 31 | 50% Advance / 50% after Installation |  | Sample data
QT-0110 | PSIL-PR-2026-0042 | Cow Nappa Upper Leather | PSIL-PO-2026-0042 | Savar Leather Works Ltd | 2026-10-05 | 2.45 | USD | 25 | 50% Advance / 50% after Installation |  | Sample data
QT-0111 | PSIL-PR-2026-0043 | Pig Lining Leather |  | Savar Leather Works Ltd | 2026-10-08 | 90.24 | BDT | 28 | Credit 30 Days |  | Sample data
QT-0112 | PSIL-PR-2026-0043 | Pig Lining Leather |  | Chattogram Packaging Ltd | 2026-10-11 | 105.74 | BDT | 53 | 50% Advance / 50% after Installation |  | Sample data
QT-0113 | PSIL-PR-2026-0044 | Primer & Halogenating Agent |  | Gazipur Chem Trade | 2026-10-09 | 507 | BDT | 9 | Credit 60 Days |  | Sample data
QT-0114 | PSIL-PR-2026-0044 | Primer & Halogenating Agent |  | Narayanganj Board Mills | 2026-10-09 | 487 | BDT | 13 | 30% Advance / 70% after In-house |  | Sample data
QT-0115 | PSIL-PR-2026-0044 | Primer & Halogenating Agent |  | Chattogram Packaging Ltd | 2026-10-09 | 525 | BDT | 34 | Credit 60 Days |  | Sample data

## Invoices
ID | PR No | Item / Material Purchased | PO No | Supplier Invoice No | Invoice Date | Qty Invoiced | Unit Price (PO Currency) | Invoice Amount incl. Tax (BDT) | Remarks | Entered By | Entered At
INV-0001 | PSIL-PR-2026-0001 | Cow Nappa Upper Leather | PSIL-PO-2026-0001 | SLW/2907 | 2026-06-16 | 10500 | 2.35 | 3160867.5 |  | Sample data
INV-0002 | PSIL-PR-2026-0003 | Pig Lining Leather | PSIL-PO-2026-0003 | SLW/2668 | 2026-07-03 | 8400 | 97 | 855540 |  | Sample data
INV-0003 | PSIL-PR-2026-0004 | PU Synthetic Leather | PSIL-PO-2026-0004 | DST/2604 | 2026-07-29 | 7400 | 3.11 | 3228864.2 |  | Sample data
INV-0004 | PSIL-PR-2026-0005 | Rubber Outsole – Men's Derby | PSIL-PO-2026-0005 | BSI/2624 | 2026-07-09 | 10439 | 186 | 2038736.7 |  | Sample data
INV-0005 | PSIL-PR-2026-0007 | EVA Midsole Sheet | PSIL-PO-2026-0007 | DST/2610 | 2026-08-14 | 4800 | 10.1 | 947784 |  | Sample data
INV-0006 | PSIL-PR-2026-0008 | PU Adhesive (Solvent Based) | PSIL-PO-2026-0008 | GCT/2919 | 2026-07-26 | 1064 | 431 | 492977.8 |  | Sample data
INV-0007 | PSIL-PR-2026-0009 | Primer & Halogenating Agent | PSIL-PO-2026-0009 | GCT/2865 | 2026-07-11 | 700 | 566 | 425915 |  | Sample data
INV-0008 | PSIL-PR-2026-0010 | Bonded Nylon Thread | PSIL-PO-2026-0010 | DT&/2707 | 2026-07-24 | 1351 | 292 | 414216.6 |  | Sample data
INV-0009 | PSIL-PR-2026-0011 | Metal Eyelets & Hooks | PSIL-PO-2026-0011 | DT&/2947 | 2026-07-22 | 900 | 230 | 217350 |  | Sample data
INV-0010 | PSIL-PR-2026-0012 | Waxed Cotton Laces | PSIL-PO-2026-0012 | DT&/2922 | 2026-07-26 | 11700 | 15.15 | 186117.75 |  | Sample data
INV-0011 | PSIL-PR-2026-0013 | Cellulose Insole Board | PSIL-PO-2026-0013 | NBM/2801 | 2026-08-16 | 2000 | 336 | 705600 |  | Sample data
INV-0012 | PSIL-PR-2026-0014 | Toe Puff & Counter Sheet | PSIL-PO-2026-0014 | DST/2825 | 2026-08-29 | 3700 | 3.35 | 1739018.5 |  | Sample data
INV-0013 | PSIL-PR-2026-0015 | Shoe Box – Printed | PSIL-PO-2026-0015 | CPL/2759 | 2026-08-12 | 17300 | 39.22 | 712431.3 |  | Sample data
INV-0014 | PSIL-PR-2026-0016 | Export Carton – 5 Ply | PSIL-PO-2026-0016 | CPL/2875 | 2026-08-04 | 1500 | 141 | 222075 |  | Sample data
INV-0015 | PSIL-PR-2026-0017 | Sewing Machine Needles & Spares | PSIL-PO-2026-0017 | DS&/2868 | 2026-08-24 | 40 | 1872 | 80496 |  | Sample data
INV-0016 | PSIL-PR-2026-0018 | Safety PPE (Masks, Gloves, Goggles) | PSIL-PO-2026-0018 | DS&/2959 | 2026-08-10 | 200 | 999 | 214785 |  | Sample data
INV-0017 | PSIL-PR-2026-0019 | Computerised Post-bed Sewing Machine | PSIL-PO-2026-0019 | JFM/2711 | 2026-10-03 | 15 | 2543.07 | 5212276.27 |  | Sample data
INV-0018 | PSIL-PR-2026-0020 | Leather Skiving Machine | PSIL-PO-2026-0020 | JFM/2675 | 2026-10-03 | 3 | 3837.39 | 1573022.91 |  | Sample data
INV-0019 | PSIL-PR-2026-0021 | Hydraulic Sole Pressing Machine | PSIL-PO-2026-0021 | JFM/2807 | 2026-10-03 | 3 | 53430.12 | 3051928.45 |  | Sample data
INV-0020 | PSIL-PR-2026-0022 | Screw Air Compressor 30 HP | PSIL-PO-2026-0022 | DS&/2875 | 2026-08-29 | 1 | 1495361 | 1607513.07 |  | Sample data
INV-0021 | PSIL-PR-2026-0023 | Laptop for PPC & Costing Team | PSIL-PO-2026-0023 | TPB/2718 | 2026-08-27 | 7 | 103649 | 761820.15 |  | Sample data
INV-0022 | PSIL-PR-2026-0024 | Pig Lining Leather | PSIL-PO-2026-0024 | SLW/2741 | 2026-09-10 | 11300 | 100.97 | 1198009.05 |  | Sample data
INV-0023 | PSIL-PR-2026-0025 | Safety PPE (Masks, Gloves, Goggles) | PSIL-PO-2026-0025 | DS&/2906 | 2026-09-10 | 200 | 913 | 196295 |  | Sample data
INV-0024 | PSIL-PR-2026-0027 | Sewing Machine Needles & Spares | PSIL-PO-2026-0027 | DS&/2927 | 2026-09-14 | 83 | 1856 | 165601.6 |  | Sample data
INV-0025 | PSIL-PR-2026-0031 | PU Adhesive (Solvent Based) | PSIL-PO-2026-0031 | GCT/2955 | 2026-09-20 | 1266 | 438 | 596096.1 |  | Sample data
INV-0026 | PSIL-PR-2026-0032 | TPR Outsole – Ladies Casual | PSIL-PO-2026-0032 | BSI/2612 | 2026-09-29 | 6433 | 124 | 837576.6 |  | Sample data
INV-0027 | PSIL-PR-2026-0033 | Cow Nappa Upper Leather | PSIL-PO-2026-0033 | SLW/2771 | 2026-10-03 | 15385 | 2.4 | 4729964.4 |  | Sample data
INV-0028 | PSIL-PR-2026-0034 | PU Adhesive (Solvent Based) | PSIL-PO-2026-0034 | GCT/2962 | 2026-09-19 | 1200 | 437 | 563730 |  | Sample data
INV-0029 | PSIL-PR-2026-0035 | TPR Outsole – Ladies Casual | PSIL-PO-2026-0035 | BSI/2870 | 2026-09-28 | 4700 | 125 | 616875 |  | Sample data
INV-0030 | PSIL-PR-2026-0036 | Waxed Cotton Laces | PSIL-PO-2026-0036 | DT&/2806 | 2026-10-08 | 19000 | 13.84 | 276108 |  | Sample data
INV-0031 | PSIL-PR-2026-0038 | Cellulose Insole Board | PSIL-PO-2026-0038 | NBM/2864 | 2026-10-13 | 1059 | 335 | 372503.25 |  | Sample data
INV-0032 | PSIL-PR-2026-0029 | PU Synthetic Leather | PSIL-PO-2026-0029 | DST/CI-889 | 2026-10-06 | 5200 | 3.04 | 2217862.4 | Commercial invoice with LC documents | Sample data